## topics
id | ca_sheet | ca_display | project | topic | supplier | global_status | advanced_start | advanced_end | advanced_status | digital_start | digital_end | digital_status | static_start | static_end | static_status | dynamic_start | dynamic_end | dynamic_status | delivery_start | delivery_end | delivery_status | n_active_phases | remaining_hours | weekly_load_hrs | avg_compression | complexity_score | complexity_level
1 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE ARMREST FIX COVER FRONT | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-03-20 | Ongoing | 2025-11-30 | 2026-04-28 | NS | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 5 | 33.42 | 2.14 | 0.39 | 18.9 | Très faible
2 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE ARMREST FIX COVER REAR | NOVARES | Ongoing |  |  | NC | [12 empty] | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
3 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE FRT MAG POUCH BOTTOM TRIM | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-03-20 | Ongoing | 2025-11-30 | 2026-04-28 | NS | 2025-12-28 | 2026-09-25 | NC | 2026-01-25 | 2026-11-19 | NS | 5 | 33.42 | 2.14 | 0.39 | 18.9 | Très faible
4 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE RR MAG POUCH BOTTOM TRIM | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 4 | 25.25 | 1.93 | 0.44 | 17.1 | Très faible
5 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE ARMREST FIX COVER | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 4 | 25.25 | 1.93 | 0.44 | 17.1 | Très faible
6 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE MAG POUCH BOTTOM TRIM | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-03-20 | Ongoing | 2025-11-30 | 2026-04-28 | NS | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 5 | 33.42 | 2.14 | 0.39 | 18.9 | Très faible
7 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE RR MAG POUCH BOTTOM TRIM | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 4 | 25.25 | 1.93 | 0.44 | 17.1 | Très faible
8 | MANAL | MANAL EL ARGOUBI | SP1 | HOLDER COVER PLATE MULTIFONCT SCREENING | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 4 | 25.25 | 1.93 | 0.44 | 17.1 | Très faible
9 | MANAL | MANAL EL ARGOUBI | SP1 | DRIVER LWR UNDER FACIA PANEL LINNING | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-03-20 | Ongoing | 2025-11-30 | 2026-04-28 | NS | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 5 | 33.42 | 2.14 | 0.39 | 18.9 | Très faible
10 | MANAL | MANAL EL ARGOUBI | SP1 | COVER FIXING FACIA PANEL RH-LH | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-01 | Ongoing | 2025-11-30 | 2026-04-28 | NS | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 5 | 33.42 | 2.13 | 0.39 | 18.9 | Très faible
11 | MANAL | MANAL EL ARGOUBI | SP1 | CURTAIN STEERING COLUMN ADJUSTABLE | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 4 | 25.25 | 1.93 | 0.44 | 17.1 | Très faible
12 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE BLANKING PLATE FRT | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-01 | Ongoing | 2025-11-30 | 2026-04-28 | NS | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 5 | 33.42 | 2.13 | 0.39 | 18.9 | Très faible
13 | MANAL | MANAL EL ARGOUBI | SP1 | USB CONN FINISHER | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-01 | Ongoing | 2025-11-30 | 2026-04-28 | NS | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 5 | 33.42 | 2.13 | 0.39 | 18.9 | Très faible
14 | MANAL | MANAL EL ARGOUBI | SP1 | CONSOLE RR FRONT | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | 2025-12-28 | 2026-09-25 | NS | 2026-01-25 | 2026-11-19 | NS | 4 | 25.25 | 1.93 | 0.44 | 17.1 | Très faible
15 | MANAL | MANAL EL ARGOUBI | SP1 | Cover fixing facia panel LH-RH | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | [6 empty] | 2 | 9.5 | 1.54 | 0.62 | 13.6 | Très faible
16 | MANAL | MANAL EL ARGOUBI | SP1 | Console blanking plate frt | NOVARES | Ongoing |  |  | NC | 2025-04-16 | 2026-04-20 | VAL | 2025-11-30 | 2026-05-19 | Ongoing | [6 empty] | 2 | 9.5 | 1.54 | 0.62 | 13.6 | Très faible
17 | MANAL | MANAL EL ARGOUBI | SP1 | Console RR front | NOVARES | Ongoing | [15 empty] | 0 | 0 | 0 |  | 0 | N/A
18 | MANAL | MANAL EL ARGOUBI | P1X | FRONT WHEEL ARCH TRIM GRAINED RH LH | TBD | Ongoing | 2025-03-07 | 2025-09-26 | NC | 2025-09-20 | 2025-01-11 | NS | 2025-01-11 | 2026-04-28 | NS | 2025-11-29 | 2026-09-25 | NS | 2025-12-27 | 2026-11-19 | NS | 5 | 33.42 | 1.91 | 0.33 | 16.9 | Très faible
19 | MANAL | MANAL EL ARGOUBI | P1X | REAR DOOR PROTECTOR | TBD | Ongoing | 2025-03-07 | 2025-09-26 | NC | 2025-09-20 | 2025-01-11 | NS | 2025-01-11 | 2026-04-28 | NS | 2025-11-29 | 2026-09-25 | NS | 2025-12-27 | 2026-11-19 | NS | 5 | 33.42 | 1.91 | 0.33 | 16.9 | Très faible
20 | MANAL | MANAL EL ARGOUBI | P1X | REAR LOWER DOOR PROTECTOR | TBD | Ongoing | 2025-03-07 | 2025-09-26 | NC | 2025-09-20 | 2025-01-11 | NS | 2025-01-11 | 2026-04-28 | NS | 2025-11-29 | 2026-09-25 | NS | 2025-12-27 | 2026-11-19 | NS | 5 | 33.42 | 1.91 | 0.33 | 16.9 | Très faible
21 | MANAL | MANAL EL ARGOUBI | P1X | REAR WHEEL ARCH TRIM GRAINED RH LH | TBD | Ongoing | 2025-03-07 | 2025-09-26 | NC | 2025-09-20 | 2025-01-11 | NS | 2025-01-11 | 2026-04-28 | NS | 2025-11-29 | 2026-09-25 | NS | 2025-12-27 | 2026-11-19 | NS | 5 | 33.42 | 1.91 | 0.33 | 16.9 | Très faible
22 | MANAL | MANAL EL ARGOUBI | P1X | FRONT LOWER DOOR PROTECTOR | TBD | Ongoing | 2025-03-07 | 2025-09-26 | NC | 2025-09-20 | 2025-01-11 | NS | 2025-01-11 | 2026-04-28 | NS | 2025-11-29 | 2026-09-25 | NS | 2025-12-27 | 2026-11-19 | NS | 5 | 33.42 | 1.91 | 0.33 | 16.9 | Très faible
23 | MANAL | MANAL EL ARGOUBI | P1H | TAILGATE LATERAL COVER | ROECHLING | Ongoing |  |  | NC | 2025-08-07 | 2026-04-01 | Ongoing | 2025-11-15 | 2026-04-28 | NS | 2025-12-13 | 2026-09-25 | NS | 2026-10-01 | 2026-11-19 | NS | 5 | 33.42 | 3.03 | 0.77 | 26.9 | Faible
24 | MANAL | MANAL EL ARGOUBI | O1H | ROCKER TRIM | TBD | Ongoing | 2025-06-25 | 2025-09-26 | NC | 2025-10-27 | 2025-03-11 | NS | 2026-03-11 | 2026-08-28 | NS | 2025-01-12 | 2026-09-25 | NS | 2025-12-29 | 2026-11-19 | NS | 5 | 33.42 | 2.09 | 0.36 | 18.5 | Très faible
25 | MANAL | MANAL EL ARGOUBI | CMP | SP 2000041337-Ressourcing-CMP REAR YOKE | zhongren | Validated |  |  | VAL |  |  | NC |  |  |  | 2025-04-16 | 2026-09-25 | VAL | 2026-03-19 | 2026-05-06 | Ongoing | 2 | 15.42 | 2.42 | 1.67 | 21.4 | Faible
26 | MANAL | MANAL EL ARGOUBI | CMP | SP 2000053575-Ressourcing-CMP Rear Wheel Bearing Gen3 | ILJIN | Validated |  |  | VAL |  |  | NC |  |  |  | 2025-04-16 | 2026-09-25 | VAL | 2026-12-03 | 2026-01-06 | Ongoing | 2 | 15.42 | 1.81 | 1 | 16.1 | Très faible
27 | MANAL | MANAL EL ARGOUBI | P1X | Seat Trim Cover RB 40% | TBD | Ongoing |  |  | Ongoing |  |  | NS | [9 empty] | 2 | 10.67 | 2.61 | 1 | 23.1 | Faible
28 | MANAL | MANAL EL ARGOUBI | P1X | Seat Trim Cover RB 60% | TBD | Ongoing |  |  | Ongoing | [12 empty] | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
29 | MANAL | MANAL EL ARGOUBI | P1X | Seat Trim Cover RCB 100% | TBD | Ongoing |  |  | Ongoing | [12 empty] | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
30 | MANAL | MANAL EL ARGOUBI | P1X | Gutter Channel Embellisher - jupe feu ar D | TBD | Ongoing |  |  | Ongoing |  |  | NS | [9 empty] | 2 | 10.67 | 2.61 | 1 | 23.1 | Faible
31 | MANAL | MANAL EL ARGOUBI | P1X | Gutter Channel Embellisher - jupe feu ar G | TBD | Ongoing |  |  | Ongoing | [12 empty] | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
32 | MANAL | MANAL EL ARGOUBI | P1X | Rear Door Glasses | SGS France | Ongoing |  |  | Ongoing | 2026-04-19 | 2026-07-25 | Ongoing | [9 empty] | 2 | 10.67 | 1.84 | 0.72 | 16.3 | Très faible
33 | MANAL | MANAL EL ARGOUBI | P1X | Backlites | SGS Spain | Ongoing |  |  | Ongoing | 2026-04-19 | 2026-07-25 | Ongoing | [9 empty] | 2 | 10.67 | 1.84 | 0.72 | 16.3 | Très faible
34 | Soumaya | Soumaya el boustani | D85 | Static sealing FRT | SAARGUMI | Closed | 2023-05-30 | 2023-04-07 | NC | 2023-04-07 | 2023-08-15 | NC | 2023-08-15 | 2023-12-09 | NC | 2023-12-09 | 2023-10-10 | NC | 2025-04-21 | 2025-07-25 | VAL | 4 | 26.17 | 3.53 | 0.67 | 31.2 | Faible
35 | Soumaya | Soumaya el boustani | D85 | Static searling RR | SAARGUMI | Closed | 2023-05-30 | 2023-04-07 | NC | 2023-04-07 | 2023-08-15 | NC | 2023-08-15 | 2023-12-09 | NC | 2023-12-09 | 2023-10-10 | NC | 2025-03-02 | 2025-07-25 | VAL | 4 | 26.17 | 3.53 | 0.67 | 31.2 | Faible
36 | Soumaya | Soumaya el boustani | D85 | Headliner | ADLER | Ongoing | 2023-03-19 | 2023-04-23 | NC | 2023-04-23 | 2023-04-06 | NC | 2023-04-06 | 2023-02-07 | NC | 2023-02-07 | 2023-07-30 | NC | 2023-07-30 | 2026-03-31 | Ongoing | 5 | 33.42 | 3.42 | 0.55 | 30.3 | Faible
37 | Soumaya | Soumaya el boustani | D85 | Cielo saint gobain | SAINT GOBAIN | Ongoing | 2023-03-07 | 2023-07-08 | NC | 2023-07-08 | 2023-09-18 | NC | 2023-09-18 | 2023-10-16 | NC | 2023-10-16 | 2023-11-13 | NC | 2023-11-13 | 2026-03-31 | Ongoing | 5 | 33.42 | 4.87 | 0.77 | 43.1 | Moyen
38 | Soumaya | Soumaya el boustani | J4U | Tailgate PO | PO | Ongoing | 2023-11-30 | 2024-04-01 | NC | 2024-04-01 | 2024-02-15 | NC | 2024-02-15 | 2024-03-14 | NC | 2024-03-14 | 2024-11-04 | NC | 2024-11-04 | 2026-05-15 | Ongoing | 5 | 33.42 | 3.6 | 0.6 | 31.9 | Faible
39 | Soumaya | Soumaya el boustani | J4U | Closed Headliner Fompak | FOMPAK | Ongoing | 2023-11-12 | 2024-01-15 | NC | 2024-01-15 | 2024-02-26 | NC | 2024-02-26 | 2024-03-25 | NC | 2025-03-03 | 2025-07-07 | VAL | 2025-10-09 | 2026-05-15 | Ongoing | 4 | 24.92 | 3.62 | 0.81 | 32 | Faible
40 | Soumaya | Soumaya el boustani | J4U | Open Headliner Fompak | FOMPAK | Ongoing | 2023-11-12 | 2024-01-15 | NC | 2024-01-15 | 2024-02-26 | NC | 2024-02-26 | 2024-03-25 | NC | 2024-03-25 | 2025-09-19 | VAL | 2025-09-17 | 2026-05-15 | Ongoing | 4 | 24.92 | 3.6 | 0.8 | 31.8 | Faible
41 | Soumaya | Soumaya el boustani | J4U | Driver Airbag | AUTOLIV | closed | 2023-06-12 | 2024-10-01 | NC | 2024-10-01 | 2024-02-21 | NC | 2024-02-21 | 2024-03-20 | NC | 2024-03-20 | 2025-12-19 | NC | 2025-11-13 | 2026-01-30 | NC | 5 | 33.42 | 3.89 | 0.81 | 34.5 | Faible
42 | Soumaya | Soumaya el boustani | J4U | Passenger Airbag | AUTOLIV | Ongoing | 2023-06-12 | 2024-10-01 | NC | 2024-10-01 | 2024-02-09 | VAL | 2025-02-09 | 2025-09-30 | NC | 2025-09-30 | 2025-12-19 | VAL | 2025-11-13 | 2026-05-30 | Ongoing | 3 | 16.75 | 0.5 | 0.26 | 4.5 | Très faible
43 | Soumaya | Soumaya el boustani | J4U | Steering wheels | AUTOLIV | Closed | 2024-11-07 | 2024-08-15 | NC | 2024-08-15 | 2024-02-09 | VAL | 2025-02-09 | 2025-09-30 | NC | 2025-09-30 | 2025-11-27 | NC | 2025-11-13 | 2025-12-30 | NC | 4 | 25.25 | 3.57 | 1.07 | 31.6 | Faible
44 | Soumaya | Soumaya el boustani | J4U | Fuel flaps | MAEIR | Ongoing | 2023-06-12 | 2024-10-01 | NC | 2024-10-01 | 2024-02-21 | NC | 2024-02-21 | 2024-03-20 | NC | 2024-03-20 | 2024-04-17 | NC | 2024-04-17 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.34 | 0.83 | 47.3 | Moyen
45 | Soumaya | Soumaya el boustani | J4U | Flap housing | MAEIR | Ongoing | 2023-06-12 | 2024-10-01 | NC | 2024-10-01 | 2024-02-21 | NC | 2024-02-21 | 2024-03-20 | NC | 2024-03-20 | 2024-04-17 | NC | 2024-04-17 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.34 | 0.83 | 47.3 | Moyen
46 | Soumaya | Soumaya el boustani | J4U | charging plug housing bottom | MAEIR | Ongoing | 2023-06-12 | 2024-10-01 | NC | 2024-10-01 | 2024-02-21 | NC | 2024-02-21 | 2024-03-20 | NC | 2024-03-20 | 2024-04-17 | NC | 2024-04-17 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.34 | 0.83 | 47.3 | Moyen
47 | Soumaya | Soumaya el boustani | J4U | Ens fuel filler case | MAEIR | Ongoing | 2023-06-12 | 2024-10-01 | NC | 2024-10-01 | 2024-02-21 | NC | 2024-02-21 | 2024-03-20 | NC | 2024-03-20 | 2024-04-17 | NC | 2024-04-17 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.34 | 0.83 | 47.3 | Moyen
48 | Soumaya | Soumaya el boustani | J4U | charging plug housing | MAEIR | Ongoing | 2023-06-12 | 2024-10-01 | NC | 2024-10-01 | 2024-02-21 | NC | 2024-02-21 | 2024-03-20 | NC | 2024-03-20 | 2024-04-17 | NC | 2024-04-17 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.34 | 0.83 | 47.3 | Moyen
49 | Soumaya | Soumaya el boustani | J4U | Door panels FRT / RR | YANFENG | Ongoing | 2023-07-12 | 2024-11-01 | NC | 2024-11-01 | 2024-02-22 | NC | 2024-02-22 | 2024-03-21 | NC | 2024-03-21 | 2024-04-18 | NC | 2024-04-18 | 2026-05-15 | Ongoing | 5 | 33.42 | 5.34 | 0.84 | 47.3 | Moyen
50 | Soumaya | Soumaya el boustani | J4U | FRT wheel flare | SAPA | Ongoing | 2023-07-12 | 2024-11-01 | NC | 2024-11-01 | 2024-02-22 | NC | 2024-02-22 | 2024-03-21 | NC | 2024-03-21 | 2024-04-18 | VAL | 2024-04-18 | 2026-03-31 | Ongoing | 4 | 24.92 | 3.22 | 0.67 | 28.5 | Faible
51 | Soumaya | Soumaya el boustani | J4U | RR wheel flare | SAPA | Ongoing | 2023-07-12 | 2024-11-01 | NC | 2024-11-01 | 2024-02-22 | NC | 2024-02-22 | 2024-03-21 | NC | 2024-03-21 | 2024-04-18 | VAL | 2024-04-18 | 2026-03-31 | Ongoing | 4 | 24.92 | 3.22 | 0.67 | 28.5 | Faible
52 | Soumaya | Soumaya el boustani | J4U | FRT door cladding | SAPA | Ongoing | 2023-07-12 | 2024-11-01 | NC | 2024-11-01 | 2024-02-22 | NC | 2024-02-22 | 2024-03-21 | NC | 2024-03-21 | 2024-04-18 | VAL | 2024-04-18 | 2026-03-31 | Ongoing | 4 | 24.92 | 3.22 | 0.67 | 28.5 | Faible
53 | Soumaya | Soumaya el boustani | J4U | RR door cladding | SAPA | Ongoing | 2023-07-12 | 2024-11-01 | NC | 2024-11-01 | 2024-02-22 | NC | 2024-02-22 | 2024-03-21 | NC | 2024-03-21 | 2024-04-18 | VAL | 2024-04-18 | 2026-03-31 | Ongoing | 4 | 24.92 | 3.22 | 0.67 | 28.5 | Faible
54 | Soumaya | Soumaya el boustani | J4U | Arm blades Passenger | FEURER | Closed | 2025-05-05 | 2025-09-06 | NC | 2025-09-06 | 2025-07-21 | NC | 2025-07-21 | 2025-08-18 | NC | 2025-08-18 | 2025-08-07 | VAL | 2025-08-07 | 2025-12-30 | VAL | 3 | 17.67 | 3.25 | 0.87 | 28.8 | Faible
55 | Soumaya | Soumaya el boustani | J4U | Arm blades driver | FEURER | Closed | 2025-05-05 | 2025-09-06 | NC | 2025-09-06 | 2025-07-21 | NC | 2025-07-21 | 2025-08-18 | NC | 2025-08-18 | 2025-08-07 | VAL | 2025-08-07 | 2025-12-30 | VAL | 3 | 17.67 | 3.25 | 0.87 | 28.8 | Faible
56 | Soumaya | Soumaya el boustani | J4U | Roof panel Lasim | LASIM | Ongoing | 2024-03-14 | 2024-04-18 | NC | 2024-04-18 | 2024-05-30 | NC | 2024-05-30 | 2024-06-27 | NC | 2024-06-27 | 2024-07-25 | NC | 2024-07-25 | 2026-04-27 | NS | 5 | 33.42 | 5.82 | 0.91 | 51.5 | Moyen
57 | Soumaya | Soumaya el boustani | J4U | Rear panel assy | PROMA | Ongoing | 2024-03-13 | 2024-04-17 | NC | 2024-04-17 | 2024-05-29 | NC | 2024-05-29 | 2024-06-26 | NC | 2024-06-26 | 2024-07-24 | NC | 2024-07-24 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.81 | 0.91 | 51.4 | Moyen
58 | Soumaya | Soumaya el boustani | J4U | Reinforcement cent | PROMA | Ongoing | 2024-03-13 | 2024-04-17 | NC | 2024-04-17 | 2024-05-29 | NC | 2024-05-29 | 2024-06-26 | NC | 2024-06-26 | 2024-07-24 | NC | 2024-07-24 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.81 | 0.91 | 51.4 | Moyen
59 | Soumaya | Soumaya el boustani | J4U | Reinforcement Av | PROMA | Ongoing | 2024-03-13 | 2024-04-17 | NC | 2024-04-17 | 2024-05-29 | NC | 2024-05-29 | 2024-06-26 | NC | 2024-06-26 | 2024-07-24 | NC | 2024-07-24 | 2026-05-30 | Ongoing | 5 | 33.42 | 5.81 | 0.91 | 51.4 | Moyen
60 | Soumaya | Soumaya el boustani | J4U | CCB | PROMA | Ongoing | 2024-01-10 | 2024-05-11 | NC | 2024-05-11 | 2024-12-17 | NC | 2024-12-17 | 2025-01-14 | NC | 2025-01-14 | 2025-11-02 | NC | 2025-11-02 | 2026-05-30 | Ongoing | 5 | 33.42 | 2.6 | 0.5 | 23 | Faible
61 | Soumaya | Soumaya el boustani | J4U | Renfort longeron | SNOP | Ongoing | 2024-05-21 | 2024-06-25 | NC | 2024-06-25 | 2024-06-08 | NC | 2024-06-08 | 2024-03-09 | NC | 2024-03-09 | 2024-01-10 | NC | 2024-01-10 | 2026-04-27 | Ongoing | 5 | 33.42 | 4.51 | 0.71 | 39.9 | Faible
62 | Soumaya | Soumaya el boustani | J4U | windshield | FUYAO | Closed | 2024-02-09 | 2024-07-10 | NC | 2024-06-25 | 2024-06-08 | NC | 2024-06-08 | 2024-03-09 | NC | 2024-12-16 | 2025-01-13 | VAL | 2025-02-07 | 2025-12-30 | NC | 4 | 24.92 | 2.8 | 0.61 | 24.8 | Faible
63 | Soumaya | Soumaya el boustani | L74 | Protecteur Porte FRT /RR Door Trim D/G | ADPLASTIK | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2026-01-04 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.93 | 0.83 | 43.7 | Moyen
64 | Soumaya | Soumaya el boustani | L74 | Elargisseur Aile AV/AR L/R | ADPLASTIK | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2026-01-04 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.93 | 0.83 | 43.7 | Moyen
65 | Soumaya | Soumaya el boustani | L74 | TAPIS AV/AR Plancher | ADLER | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-10-07 | 2025-12-12 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.14 | 0.72 | 36.6 | Faible
66 | Soumaya | Soumaya el boustani | L74 | Garniture Pavillon TN/TO | ADLER | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-10-07 | 2025-11-28 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.38 | 0.75 | 38.8 | Faible
67 | Soumaya | Soumaya el boustani | L74 | GLASSE ROOF | FUYAO | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2025-12-12 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 8.19 | 1.29 | 72.5 | Fort
68 | Soumaya | Soumaya el boustani | L74 | Panneau garniture Porte AV/AR D/G | ANTOLIN | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2026-01-04 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.93 | 0.83 | 43.7 | Moyen
69 | Soumaya | Soumaya el boustani | L74 | SPOILER | FLEXNGATE | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | VAL | 2025-09-30 | 2025-11-30 | NC | 2025-11-16 | 2025-12-12 | VAL | 2026-01-04 | 2026-06-24 | Ongoing | 3 | 16.75 | 1.6 | 0.58 | 14.2 | Très faible
70 | Soumaya | Soumaya el boustani | L74 | AEROFIN | FLEXNGATE | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | VAL | 2025-09-30 | 2025-11-30 | NC | 2025-11-16 | 2025-12-12 | VAL | 2026-01-04 | 2026-06-24 | Ongoing | 3 | 16.75 | 1.6 | 0.58 | 14.2 | Très faible
71 | Soumaya | Soumaya el boustani | L74 | Tailgate | FLEXNGATE | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | VAL | 2025-09-30 | 2025-11-30 | NC | 2025-11-16 | 2025-12-12 | VAL | 2026-01-04 | 2026-06-24 | Ongoing | 3 | 16.75 | 1.6 | 0.58 | 14.2 | Très faible
72 | Soumaya | Soumaya el boustani | L74 | BACKLIGHT | FUYAO | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-16 | 2025-12-12 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 5.52 | 0.91 | 48.9 | Moyen
73 | Soumaya | Soumaya el boustani | L74 | Static sealing FRT | SAARGUMI | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2026-01-04 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.93 | 0.83 | 43.7 | Moyen
74 | Soumaya | Soumaya el boustani | L74 | Rear panel assy | TIBERINA | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2026-01-04 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.93 | 0.83 | 43.7 | Moyen
75 | Soumaya | Soumaya el boustani | L74 | BPILLAR | TIBERINA | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2026-01-04 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.93 | 0.83 | 43.7 | Moyen
76 | Soumaya | Soumaya el boustani | D74 | Tailgate | FlexnGate | Ongoing | 2024-06-26 | 2024-07-31 | NC | 2024-06-26 | 2024-07-08 | VAL | 2024-04-07 | 2024-01-08 | VAL | 2025-01-22 | 2025-10-30 | VAL | 2025-02-10 | 2026-04-20 | Ongoing | 2 | 9.75 | 0.62 | 0.33 | 5.5 | Très faible
77 | Soumaya | Soumaya el boustani | D74 | Aerofins RH/LH | FlexnGate | Ongoing | 2024-03-07 | 2024-07-08 | NC | 2024-03-07 | 2024-08-14 | VAL | 2024-06-09 | 2024-04-10 | VAL | 2025-01-22 | 2025-02-19 | VAL | 2025-02-04 | 2026-04-20 | Ongoing | 2 | 9.75 | 0.26 | 0.18 | 2.3 | Très faible
78 | Soumaya | Soumaya el boustani | D74 | Spoiler | FlexnGate | Ongoing | 2024-04-07 | 2024-08-08 | NC | 2024-04-07 | 2024-08-15 | VAL | 2024-06-09 | 2024-04-10 | VAL | 2025-02-04 | 2025-04-30 | VAL | 2025-02-07 | 2026-04-20 | Ongoing | 2 | 9.75 | 0.26 | 0.19 | 2.3 | Très faible
79 | Soumaya | Soumaya el boustani | D74 | RR Door LH/RH | Antolin | Ongoing | 2024-12-09 | 2024-10-17 | NC | 2024-12-09 | 2025-10-09 | VAL | 2025-04-09 | 2025-02-10 | VAL | 2024-11-22 | 2024-12-20 | VAL | 2025-02-19 | 2026-05-14 | Ongoing | 2 | 9.75 | 1.36 | 0.62 | 12.1 | Très faible
80 | Soumaya | Soumaya el boustani | D74 | RR WAC LH/RH | Adplastik | Closed | 2024-09-19 | 2024-10-24 | NC | 2024-09-19 | 2025-10-09 | VAL | 2025-04-09 | 2025-02-10 | VAL | 2024-11-20 | 2025-07-25 | VAL | 2025-08-27 | 2025-12-19 | VAL | 1 | 2.5 | 0.5 | 0.4 | 4.4 | Très faible
81 | Soumaya | Soumaya el boustani | D74 | RR Door TRIM LH/RH | Adplastik | Closed | 2024-09-16 | 2024-10-21 | NC | 2024-09-16 | 2025-10-09 | VAL | 2025-04-09 | 2025-02-10 | VAL | 2024-11-20 | 2025-07-25 | VAL | 2025-08-27 | 2025-12-19 | VAL | 1 | 2.5 | 0.5 | 0.4 | 4.4 | Très faible
82 | Soumaya | Soumaya el boustani | D74 | Headliner NR/SR | Adler | Ongoing | 2024-12-09 | 2024-10-17 | NC | 2024-12-09 | 2024-10-24 | VAL | 2024-10-30 | 2025-09-25 | VAL | 2025-11-09 | 2025-12-04 | VAL | 2025-09-30 | 2026-06-14 | NS | 2 | 9.75 | 1.45 | 0.72 | 12.8 | Très faible
83 | Soumaya | Soumaya el boustani | D74 | Glass Channel FRT LH/RH | Sargummi | Ongoing | 2025-04-28 | 2025-02-06 | NC | 2025-04-28 | 2025-09-06 | VAL | 2025-11-05 | 2025-11-09 | NC | 2025-11-09 | 2025-08-30 | VAL | 2025-08-29 | 2026-04-30 | Ongoing | 3 | 16.75 | 13.71 | 3.99 | 100 | Très fort
84 | Soumaya | Soumaya el boustani | D74 | Glass Channel RR | Sargummi | Ongoing | 2025-04-28 | 2025-02-06 | NC | 2025-04-28 | 2025-09-06 | VAL | 2025-11-05 | 2025-11-09 | NC | 2025-11-09 | 2026-02-15 | VAL | 2025-11-26 | 2026-04-30 | Ongoing | 3 | 16.75 | 13.83 | 4.07 | 100 | Très fort
85 | Soumaya | Soumaya el boustani | D74 | RR Panel Ass | TIBERINA | Ongoing | 2024-04-09 | 2024-09-10 | NC | 2024-04-09 | 2025-10-09 | VAL | 2025-04-09 | 2025-02-10 | VAL | 2024-12-11 | 2024-10-12 | VAL | 2025-07-02 | 2026-06-14 | Ongoing | 2 | 9.75 | 0.26 | 0.21 | 2.3 | Très faible
86 | Soumaya | Soumaya el boustani | D74 | B Pillar LH/RH | TIBERINA | closed | 2024-09-16 | 2024-10-21 | NC | 2024-09-16 | 2025-10-09 | VAL | 2025-04-09 | 2025-02-10 | VAL | 2025-07-02 | 2025-07-03 | VAL | 2025-02-27 | 2026-02-20 | VAL | 1 | 2.5 | 0.5 | 0.4 | 4.4 | Très faible
87 | Soumaya | Soumaya el boustani | D74 | Cielo | FUYAO | Ongoing | 2024-04-09 | 2024-09-10 | NC | 2024-04-09 | 2024-10-16 | VAL | 2024-04-09 | 2025-10-16 | VAL | 2025-11-09 | 2025-12-10 | VAL | 2025-09-30 | 2026-04-30 | Ongoing | 2 | 9.75 | 0.35 | 0.31 | 3.1 | Très faible
88 | Soumaya | Soumaya el boustani | D74 | RR ROOF Crossember | LASIM | Ongoing | 2024-09-19 | 2024-10-24 | NC | 2024-09-19 | 2025-01-10 | VAL | 2025-01-10 | 2025-10-29 | VAL | 2025-06-19 | 2025-11-26 | VAL | 2025-09-26 | 2026-04-30 | NS | 2 | 9.75 | 0.73 | 0.46 | 6.5 | Très faible
97 | Soumaya | Soumaya el boustani | L74 | CO Headup displays | Panasonic | Ongoing | 2025-07-22 | 2025-08-26 | NC | 2025-08-26 | 2025-09-30 | NC | 2025-09-30 | 2025-11-30 | NC | 2025-11-30 | 2026-01-04 | NC | 2026-01-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 4.93 | 0.83 | 43.7 | Moyen
98 | Soumaya | Soumaya el boustani | J4U | Floor carpet CO | ADLER | Closed | 2024-02-09 | 2024-07-10 | NC | 2024-06-25 | 2024-06-08 | NC | 2024-06-08 | 2024-03-09 | NC | 2025-01-14 | 2025-11-02 | NC | 2025-11-02 | 2025-12-12 | VAL | 4 | 26.17 | 2.85 | 0.56 | 25.2 | Faible
99 | Soumaya | Soumaya el boustani | J4U | Dash inner CO | ADLER | Closed | 2024-02-09 | 2024-07-10 | NC | 2024-06-25 | 2024-06-08 | NC | 2024-06-08 | 2024-03-09 | NC | 2024-03-09 | 2024-01-10 | NC | 2024-01-10 | 2025-12-12 | VAL | 4 | 26.17 | 4.06 | 0.77 | 35.9 | Faible
100 | Soumaya | Soumaya el boustani | D74 | REAR BEZEL ENDCAP | Sigit | Ongoing |  | 1900-04-02 | NC | 1900-04-02 | 2025-11-06 | VAL | 2025-11-06 | 2026-02-20 | Ongoing | 2026-02-20 | 2026-04-03 | NS | 2026-04-03 | 2026-06-26 | NS | 4 | 25.25 | 3.73 | 0.93 | 33 | Faible
101 | Soumaya | Soumaya el boustani | D74 | UPPER ARMATURE COVER WLC FAN ASSY | Sigit | Closed |  | 1900-04-02 | NC | 1900-04-02 | 2025-11-06 | NC | 2025-11-06 | 2025-12-18 | NC | 2025-12-18 | 2026-01-29 | NC | 2026-01-29 | 2026-04-23 | NC | 5 | 33.42 | 4.44 | 0.87 | 39.3 | Faible
102 | Soumaya | Soumaya el boustani | D74 | HFASM BRACKET ASSY | Sigit | Closed |  | 1900-04-02 | NC | 1900-04-02 | 2025-11-06 | NC | 2025-11-06 | 2025-12-18 | NC | 2025-12-18 | 2026-01-29 | NC | 2026-01-29 | 2026-04-23 | NC | 5 | 33.42 | 4.44 | 0.87 | 39.3 | Faible
103 | Soumaya | Soumaya el boustani | D74 | STORAGE BOX ASSY | Sigit | Closed |  | 1900-04-02 | NC | 1900-04-02 | 2025-11-06 | NC | 2025-11-06 | 2025-12-18 | NC | 2025-12-18 | 2026-01-29 | NC | 2026-01-29 | 2026-04-23 | NC | 5 | 33.42 | 4.44 | 0.87 | 39.3 | Faible
104 | Soumaya | Soumaya el boustani | D74 | PALMAREST ASSY | Sigit | Closed |  | 1900-04-02 | NC | 1900-04-02 | 2025-11-06 | NC | 2025-11-06 | 2025-12-18 | NC | 2025-12-18 | 2026-01-29 | NC | 2026-01-29 | 2026-04-23 | NC | 5 | 33.42 | 4.44 | 0.87 | 39.3 | Faible
105 | Soumaya | Soumaya el boustani | D74 | COVER LOWER ARMATUR | Sigit | Closed |  | 1900-04-02 | NC | 1900-04-02 | 2025-11-06 | NC | 2025-11-06 | 2025-12-18 | NC | 2025-12-18 | 2026-01-29 | NC | 2026-01-29 | 2026-04-23 | NC | 5 | 33.42 | 4.44 | 0.87 | 39.3 | Faible
106 | Soumaya | Soumaya el boustani | D74 | FRT Door LH/RH | Antolin | Ongoing |  |  |  | 2024-12-09 | 2025-10-09 | VAL | 2025-04-09 | 2025-02-10 | VAL | 2024-11-22 | 2024-12-20 | VAL | 2025-02-19 | 2026-05-14 | Ongoing | 1 | 7.25 | 0.11 | 0.25 | 1 | Très faible
107 | Soumaya | Soumaya el boustani | D74 | REAR CONSOLE | Sigit | Ongoing |  |  |  | 1900-04-02 | 2025-11-06 | NC | 2025-11-06 | 2025-12-18 | NC | 2025-12-18 | 2026-01-29 | NC | 2026-01-29 | 2026-06-14 | Ongoing | 4 | 30.92 | 2.96 | 0.71 | 26.2 | Faible
108 | MOFIDA | MOFIDA EL HABTI | F1H | Seats assemblyF1H | Marturfompak | Ongoing | 2025-04-02 |  | VAL | 2025-08-04 | 2025-10-10 | VAL |  | 2026-03-04 | Ongoing | 2026-03-04 | 2026-04-15 | Ongoing | 2026-04-15 | 2026-07-08 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
109 | MOFIDA | MOFIDA EL HABTI | K9 | Rear seats K9 | Marturfompak |  | 2025-10-26 | 2025-11-26 |  | 2025-10-19 | 2026-03-26 | Ongoing | 2026-03-26 | 2026-05-07 |  | 2026-05-07 | 2026-06-18 |  | 2026-06-18 | 2026-09-10 | NS | 2 | 15.42 | 0.97 | 0.8 | 8.6 | Très faible
110 | MOFIDA | MOFIDA EL HABTI | K9 | Seats assembly K9 | Marturfompak |  | 2025-02-04 | 2025-10-23 |  | 2025-09-26 | 2025-10-31 | NC |  | 2026-03-02 | NC | 2026-03-02 | 2026-04-13 | NC | 2026-04-13 | 2026-07-06 | NC | 4 | 30.92 | 4.82 | 1.13 | 42.7 | Moyen
111 | MOFIDA | MOFIDA EL HABTI | F1H | Exhaust F1H | Purem |  | 2025-01-27 |  | VAL | 2025-02-21 | 2025-10-17 | VAL | 2026-01-15 | 2026-01-29 | VAL | 2026-01-29 | 2026-03-31 | Ongoing | 2026-03-31 | 2026-06-23 | NS | 2 | 15.75 | 1.58 | 1.01 | 14 | Très faible
112 | MOFIDA | MOFIDA EL HABTI | K9 | Exhaust K9 | Purem |  | 2025-01-27 | 2025-10-16 |  | 2025-09-26 | 2025-11-03 | VAL | 2026-01-15 | 2026-01-29 | VAL | 2026-01-29 | 2026-03-31 | Ongoing | 2026-03-31 | 2026-06-23 | NS | 2 | 15.75 | 1.58 | 1.01 | 14 | Très faible
113 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Wheels K9/F1H | Ferruz |  | 2025-02-12 |  | VAL | 2025-05-14 | 2025-10-03 | VAL |  | 2025-10-10 | VAL | 2025-07-04 | 2025-10-10 | VAL | 2025-10-10 | 2026-03-24 | Ongoing | 1 | 7.25 | 0.31 | 0.68 | 2.7 | Très faible
114 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Rear UBS HIGH ASSY | Sarel |  | 2025-05-06 |  | VAL | 2025-06-13 | 2025-10-24 | VAL |  | 2026-03-17 | Ongoing | 2026-03-17 | 2026-04-28 | Ongoing | 2026-04-28 | 2026-07-21 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
115 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Rear console ASSY | Sarel |  | 2025-05-06 |  | VAL | 2025-06-13 | 2025-10-24 | VAL |  | 2026-03-17 | Ongoing | 2026-03-17 | 2026-04-28 | Ongoing | 2026-04-28 | 2026-07-21 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
116 | MOFIDA | MOFIDA EL HABTI | K9/F1H | ASSEMBLY ICE LINGOTTO BEZLE | Sarel |  | 2025-05-06 |  | VAL | 2025-06-13 | 2025-10-24 | VAL |  | 2026-03-17 | Ongoing | 2026-03-17 | 2026-04-28 | Ongoing | 2026-04-28 | 2026-07-21 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
117 | MOFIDA | MOFIDA EL HABTI | K9/F1H | FRONT BEZEL ASSY | Sarel |  | 2025-05-06 |  | VAL | 2025-06-13 | 2025-10-24 | VAL |  | 2026-03-17 | Ongoing | 2026-03-17 | 2026-04-28 | Ongoing | 2026-04-28 | 2026-07-21 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
118 | MOFIDA | MOFIDA EL HABTI | K9/F1H | LEFT COVER ASSY | Sarel |  | 2025-05-06 |  | VAL | 2025-06-13 | 2025-10-24 | VAL |  | 2026-03-17 | Ongoing | 2026-03-17 | 2026-04-28 | Ongoing | 2026-04-28 | 2026-07-21 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
119 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Door panels F1H | SIGIT |  | 2025-05-21 | 2025-08-31 | VAL | 2025-08-27 | 2026-03-19 | Ongoing | 2026-03-19 | 2026-04-30 | Ongoing | 2026-04-30 | 2026-06-11 | Ongoing | 2026-06-11 | 2026-09-03 | NS | 4 | 30.92 | 3.47 | 0.88 | 30.7 | Faible
120 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Door panels K9 | SIGIT |  | 2025-05-21 | 2025-08-31 | VAL | 2025-08-27 | 2026-03-19 | Ongoing | 2026-03-19 | 2026-04-30 | Ongoing | 2026-04-30 | 2026-06-11 | Ongoing | 2026-06-11 | 2026-09-03 | NS | 4 | 30.92 | 3.47 | 0.88 | 30.7 | Faible
121 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Bumpers K9 |  |  | 2025-03-21 | 2025-10-20 |  | 2026-03-10 | 2026-04-07 |  | 2026-04-07 | 2026-05-19 | NS | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
122 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Bumpers F1H |  |  | 2025-03-22 | 2025-10-20 |  | 2026-03-10 | 2026-04-07 |  | 2026-04-07 | 2026-05-19 | NS | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
123 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Load floor Stamping parts |  |  | 2025-06-05 | 2025-10-20 |  | 2026-03-01 | 2026-03-29 | Ongoing | 2026-03-29 | 2026-05-10 | Ongoing | 2026-05-10 | 2026-06-21 | Ongoing | 2026-06-21 | 2026-09-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
124 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Dashboard assembly F1H |  |  | 2025-05-28 | 2025-10-09 |  | 2026-03-10 | 2026-04-07 | CANCELED | 2026-04-07 | 2026-05-19 | NS | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
125 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Dashboard assembly K9 |  |  | 2025-06-05 | 2025-10-09 |  | 2026-03-10 | 2026-04-07 | CANCELED | 2026-04-07 | 2026-05-19 | NS | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
126 | MOFIDA | MOFIDA EL HABTI | K9/F1H | TRIM LWR PILLAR CENT RH/LH |  |  | 2025-06-05 | 2025-09-18 | VAL | 2025-08-10 | 2026-03-25 | NC | 2026-03-25 | 2026-05-06 | Ongoing | 2026-05-06 | 2026-06-17 | Ongoing | 2026-06-17 | 2026-09-09 | NS | 4 | 30.92 | 3.44 | 0.88 | 30.4 | Faible
127 | MOFIDA | MOFIDA EL HABTI | K9/F1H | TRIM LWR PILLAR CENT RH/LH |  |  | 2025-06-05 | 2025-09-18 | VAL | 2025-08-11 | 2026-03-25 | NC | 2026-03-25 | 2026-05-06 | Ongoing | 2026-05-06 | 2026-06-17 | Ongoing | 2026-06-17 | 2026-09-09 | NS | 4 | 30.92 | 3.44 | 0.88 | 30.5 | Faible
128 | MOFIDA | MOFIDA EL HABTI | K9/F1H | TRIM UPR PILLAR CENT RH/LH |  |  | 2025-06-05 | 2025-09-18 | VAL | 2025-08-12 | 2026-03-25 | NC | 2026-03-25 | 2026-05-06 | Ongoing | 2026-05-06 | 2026-06-17 | Ongoing | 2026-06-17 | 2026-09-09 | NS | 4 | 30.92 | 3.44 | 0.88 | 30.5 | Faible
129 | MOFIDA | MOFIDA EL HABTI | K9/F1H | FRONT PILLAR TRIM RH LH |  |  | 2025-06-05 | 2025-09-18 | VAL | 2025-08-13 | 2026-03-25 | NC | 2026-03-25 | 2026-05-06 | Ongoing | 2026-05-06 | 2026-06-17 | Ongoing | 2026-06-17 | 2026-09-09 | NS | 4 | 30.92 | 3.44 | 0.88 | 30.5 | Faible
130 | MOFIDA | MOFIDA EL HABTI | K9/F1H | TRIM UPR PILLAR CENT RH/LH |  |  | 2025-06-05 | 2025-09-18 | VAL | 2025-08-14 | 2026-03-25 | NC | 2026-03-25 | 2026-05-06 | Ongoing | 2026-05-06 | 2026-06-17 | Ongoing | 2026-06-17 | 2026-09-09 | NS | 4 | 30.92 | 3.44 | 0.88 | 30.5 | Faible
131 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Trim tailgate |  |  | 2025-06-05 | 2025-09-18 | VAL | 2026-03-10 | 2026-04-07 | Ongoing | 2026-04-07 | 2026-05-19 |  | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 23.92 | 4.06 | 1.28 | 36 | Faible
132 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Trim tailgate 2 |  |  | 2025-06-05 | 2025-09-18 | VAL | 2026-03-10 | 2026-04-07 | Ongoing | 2026-04-07 | 2026-05-19 |  | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 23.92 | 4.06 | 1.28 | 36 | Faible
133 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Trim tailgate 3 |  |  | 2025-06-05 | 2025-09-18 | VAL | 2026-03-10 | 2026-04-07 | Ongoing | 2026-04-07 | 2026-05-19 |  | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 23.92 | 4.06 | 1.28 | 36 | Faible
134 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Trim tailgate 4 |  |  | 2025-06-05 | 2025-09-18 | VAL | 2026-03-10 | 2026-04-07 | Ongoing | 2026-04-07 | 2026-05-19 |  | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 23.92 | 4.06 | 1.28 | 36 | Faible
135 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Trim REAR quarter |  |  | 2025-06-05 | 2025-09-18 | VAL | 2026-03-10 | 2026-04-07 | Ongoing | 2026-04-07 | 2026-05-19 |  | 2026-05-19 | 2026-06-30 | NS | 2026-06-30 | 2026-09-22 | NS | 3 | 23.92 | 4.06 | 1.28 | 36 | Faible
136 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Stamping parts F1H |  |  | 2025-07-23 | 2025-09-26 | VAL | 2026-03-10 | 2026-04-07 | VAL | 2026-04-07 | 2026-05-19 | NC | 2026-05-19 | 2026-06-30 | NC | 2026-06-30 | 2026-09-22 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
137 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Stamping parts K9 |  |  | 2025-06-11 | 2025-10-16 |  | 2026-03-10 | 2026-04-07 | VAL | 2026-04-07 | 2026-05-19 | NC | 2026-05-19 | 2026-06-30 | NC | 2026-06-30 | 2026-09-22 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
138 | MOFIDA | MOFIDA EL HABTI | K9/F1H | MAIN HARNESS |  |  | 2025-05-26 |  | VAL | 2025-08-19 | 2026-03-13 | VAL | 2026-03-13 | 2026-04-24 | NC | 2026-04-24 | 2026-06-05 | NC | 2026-06-05 | 2026-08-28 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
139 | MOFIDA | MOFIDA EL HABTI | K9/F1H | SMALL HARNESS |  |  | 2025-06-16 |  | VAL | 2026-03-10 | 2026-04-07 | VAL | 2026-04-07 | 2026-05-19 | NC | 2026-05-19 | 2026-06-30 | NC | 2026-06-30 | 2026-09-22 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
140 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Parcel Shelf F1H Algeria |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
141 | MOFIDA | MOFIDA EL HABTI | K9/F1H | FLOOR CARPET ICE |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
142 | MOFIDA | MOFIDA EL HABTI | K9/F1H | TRUNK CARPET |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
143 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Front Floor insulator |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
144 | MOFIDA | MOFIDA EL HABTI | K9/F1H | REAR FLOOR INSULATOR |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
145 | MOFIDA | MOFIDA EL HABTI | K9/F1H | PARCEL SHELF |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
146 | MOFIDA | MOFIDA EL HABTI | K9/F1H | TRUNK SIDE TRIM RH |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
147 | MOFIDA | MOFIDA EL HABTI | K9/F1H | TRUNK SIDE TRIM LH |  |  | 2025-09-18 | 2025-11-01 |  | 2026-03-31 | 2026-04-28 | NS | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 4 | 30.92 | 5.23 | 1.21 | 46.3 | Moyen
148 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Stamping parts 3 |  |  | 2025-10-06 | 2025-11-09 |  | 2026-03-31 | 2026-04-28 | VAL | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
149 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Stamping parts 4 |  |  | 2025-10-06 | 2025-11-09 |  | 2026-03-31 | 2026-04-28 | VAL | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
150 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Stamping parts 5 |  |  | 2025-10-06 | 2025-11-09 |  | 2026-03-31 | 2026-04-28 | VAL | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
151 | MOFIDA | MOFIDA EL HABTI | K9/F1H | Stamping parts 6 |  |  | 2025-10-06 | 2025-11-09 |  | 2026-03-31 | 2026-04-28 | VAL | 2026-04-28 | 2026-06-09 | NS | 2026-06-09 | 2026-07-21 | NS | 2026-07-21 | 2026-10-13 | NS | 3 | 22.75 | 3.19 | 1.11 | 28.2 | Faible
152 | Ayoub | Ayoub Himich | STLAS | Heat Pump | DENSO | Ongoing | 2022-10-19 | 2022-11-23 | VAL | 2023-05-12 | 2026-03-27 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
153 | Ayoub | Ayoub Himich | STLAS | OHX | DENSO | Ongoing | 2022-10-19 | 2022-11-23 | VAL | 2023-05-12 | 2026-03-27 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
154 | Ayoub | Ayoub Himich | STLAS | COMPRESSOR | DENSO | Ongoing | 2022-10-19 | 2022-11-23 | VAL | 2023-05-12 | 2026-04-24 | NC | 2025-10-31 | 2026-04-12 | NC | 2026-12-04 | 2026-09-08 | NC | 2026-09-08 | 2026-11-01 | NC | 4 | 30.92 | 2.71 | 0.84 | 24 | Faible
155 | Ayoub | Ayoub Himich | STLAS | HVAC | SANDEN | Ongoing | 2022-10-19 | 2022-11-23 | VAL | 2023-09-07 | 2026-04-24 | Ongoing | 2025-10-31 | 2026-04-12 | NS | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 30.92 | 2.72 | 0.84 | 24 | Faible
156 | Ayoub | Ayoub Himich | STLAS | FRONT BRAKE DISC 330x24 | OMR | Ongoing | 2023-02-08 | 2023-06-09 | VAL | 2023-02-09 | 2026-01-16 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
157 | Ayoub | Ayoub Himich | STLAS | FRONT BRAKE DISC 315x24 | OMR | Ongoing | 2023-02-08 | 2023-06-09 | VAL | 2023-02-09 | 2026-01-16 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
158 | Ayoub | Ayoub Himich | STLAS | BATTERY MODULES | CATL | Ongoing | 2022-10-24 | 2022-11-28 | VAL | 2022-12-07 | 2026-02-20 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
159 | Ayoub | Ayoub Himich | STLAS | SBW HWA | JTEKT | Ongoing | 2022-10-19 | 2022-11-23 | VAL | 2022-11-28 | 2026-03-27 | VAL | 2025-10-31 | 2026-04-12 | VAL | 2026-12-04 | 2026-09-08 | Ongoing | 2026-09-08 | 2026-11-01 | NS | 2 | 15.75 | 2.36 | 1.54 | 20.9 | Faible
160 | Ayoub | Ayoub Himich | STLAS | SBW FWA | JTEKT | Ongoing | 2022-10-19 | 2022-11-23 | VAL | 2022-11-28 | 2026-02-13 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
161 | Ayoub | Ayoub Himich | STLAS | eDRUMS 10" | MOBIS | Ongoing | 2022-10-31 | 2022-05-12 | VAL | 2023-06-21 | 2026-04-24 | Ongoing | 2025-10-31 | 2026-04-12 | NS | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 30.92 | 2.71 | 0.84 | 24 | Faible
162 | Ayoub | Ayoub Himich | STLAS | eDRUMS 11" | MOBIS | Ongoing | 2022-10-31 | 2022-05-12 | VAL | 2023-06-21 | 2026-04-24 | Ongoing | 2025-10-31 | 2026-04-12 | NS | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 30.92 | 2.71 | 0.84 | 24 | Faible
163 | Ayoub | Ayoub Himich | STLAS | COOLING FAN | BROSE | Ongoing | 2023-02-08 | 2023-06-09 | VAL | 2023-04-21 | 2026-03-27 | VAL | 2025-12-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.84 | 1.16 | 25.1 | Faible
164 | Ayoub | Ayoub Himich | STLAS | TMM | HUTCHINSON | Ongoing | 2022-10-31 | 2022-05-12 | VAL | 2022-12-06 | 2026-01-30 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
165 | Ayoub | Ayoub Himich | STLAS | TBMU | MARELLI | Ongoing | 2024-06-13 | 2024-07-18 | NC | 2024-07-18 | 2025-12-19 | VAL | 2025-12-09 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 25.25 | 3.25 | 0.95 | 28.8 | Faible
166 | Ayoub | Ayoub Himich | STLAS | CMC | MARELLI | Ongoing | 2024-06-13 | 2024-07-18 | NC | 2024-07-18 | 2025-12-19 | VAL | 2025-12-09 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 25.25 | 3.25 | 0.95 | 28.8 | Faible
167 | Ayoub | Ayoub Himich | STLAS | IDCM | VALEO | Ongoing | 2022-10-09 | 2022-10-15 | VAL | 2022-02-08 | 2026-04-24 | Ongoing | 2025-10-24 | 2026-04-12 | NS | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 30.92 | 2.68 | 0.84 | 23.7 | Faible
168 | Ayoub | Ayoub Himich | STLAS | DAE LHD | NEXTEER | Ongoing | 2022-11-11 | 2022-12-16 | VAL | 2022-12-20 | 2026-04-24 | Ongoing | 2025-10-31 | 2026-04-12 | NS | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 30.92 | 2.7 | 0.84 | 23.9 | Faible
169 | Ayoub | Ayoub Himich | STLAS | DAE RHD | NEXTEER | Ongoing | 2022-11-11 | 2022-12-16 | VAL | 2022-12-20 | 2026-04-24 | Ongoing | 2025-10-31 | 2026-04-12 | NS | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 4 | 30.92 | 2.7 | 0.84 | 23.9 | Faible
170 | Ayoub | Ayoub Himich | STLAS | CROSS CAR BEAM | TIBERINA | Ongoing | 2024-06-24 | 2024-07-29 | VAL | 2025-02-25 |  | NC | 2025-10-31 | 2026-04-12 | NC | 2026-12-04 | 2026-09-08 | NC | 2026-09-08 | 2026-11-01 | NC | 4 | 30.92 | 4.02 | 1.08 | 35.6 | Faible
171 | Ayoub | Ayoub Himich | STLAS | ONEBOX | MOBIS | Ongoing | 2022-10-31 | 2022-05-12 | VAL | 2022-12-08 | 2026-02-20 | VAL | 2025-10-31 | 2026-04-12 | Ongoing | 2026-12-04 | 2026-09-08 | NS | 2026-09-08 | 2026-11-01 | NS | 3 | 22.75 | 2.66 | 1.11 | 23.5 | Faible
172 | Ayoub | Ayoub Himich | STLAS | cooling plate | Marelli | Ongoing | 2022-10-31 | 2022-05-12 | NC | 2022-12-08 | 2026-03-27 | NC | 2025-10-31 | 2026-04-12 | NC | 2026-12-04 | 2026-09-08 | NC | 2026-09-08 | 2026-11-01 | NC | 5 | 33.42 | 3.95 | 0.87 | 35 | Faible
173 | Ayoub | Ayoub Himich | STLAS | gasket lid | Tesa | Ongoing | 2022-10-31 | 2022-05-12 | NC | 2022-12-08 | 2026-03-27 | NC | 2025-10-31 | 2026-04-12 | NC | 2026-12-04 | 2026-09-08 | NC | 2026-09-08 | 2026-11-01 | NC | 5 | 33.42 | 3.95 | 0.87 | 35 | Faible
174 | KHALID | KHALID BOUHLAL | P5 MCA | HEADLAMP |  | Ongoing | 2024-03-12 | 2025-07-01 | NC | 2025-07-01 | 2025-02-18 | NC | 2025-02-18 | 2025-03-18 | NC | 2025-03-18 | 2025-07-31 | VAL | 2025-07-31 | 2026-04-03 | Ongoing | 4 | 24.92 | 3.35 | 0.75 | 29.7 | Faible
175 | KHALID | KHALID BOUHLAL | D41 MCA | FLOOR CONSOLE |  | Ongoing | 2025-01-01 | 2025-05-02 | NC | 2025-05-02 | 2025-10-01 | VAL | 2025-09-26 | 2025-10-24 | NC | 2025-10-24 | 2025-10-17 | VAL | 2026-01-26 | 2026-04-03 | Ongoing | 3 | 16.75 | 2.65 | 1.1 | 23.5 | Faible
176 | KHALID | KHALID BOUHLAL | P5 MCA | Rear lamp T1 |  | Ongoing |  |  | NC |  |  | VAL |  |  | VAL |  | 2026-01-30 | VAL | 2026-01-30 | 2026-04-24 | Ongoing | 2 | 9.75 | 1.85 | 1.17 | 16.4 | Très faible
177 | KHALID | KHALID BOUHLAL | P5 MCA | Rear lamp T3 |  | Ongoing |  |  | NC |  |  | VAL |  |  | VAL |  | 2026-01-30 | VAL | 2026-01-30 | 2026-04-24 | Ongoing | 2 | 9.75 | 1.85 | 1.17 | 16.4 | Très faible
178 | KHALID | KHALID BOUHLAL | CMP | control arm |  | Ongoing |  |  | VAL |  |  | VAL |  | 2026-01-15 | VAL | 2026-01-15 | 2026-04-09 | Ongoing | 2026-04-09 | 2026-07-02 | NS | 2 | 15.75 | 1.31 | 0.92 | 11.6 | Très faible
179 | KHALID | KHALID BOUHLAL | P21 | SUNSHADE |  | Ongoing |  |  | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-27 | 2026-04-24 | NS | 2026-04-24 | 2026-06-19 | NS | 2026-06-19 | 2026-09-11 | NS | 4 | 30.92 | 4.22 | 1.04 | 37.4 | Faible
180 | KHALID | KHALID BOUHLAL | P64 | COLONNE DE DIRECTION JTEKT | JTEKT | Ongoing |  |  | NC |  |  | VAL | 2026-01-06 | 2026-04-10 | Ongoing | 2026-04-10 | 2026-06-05 | NS | 2026-06-05 | 2026-08-28 | NS | 4 | 25.25 | 3.44 | 0.88 | 30.4 | Faible
181 | KENZA | KENZA AADAM | O2C | Bracket kit | OPM | Validated | 2024-05-03 | 2024-09-04 | NC | 2025-09-18 | 2025-10-30 | VAL |  |  | NC |  |  | NC | 2026-02-25 | 2026-02-25 | VAL | 3 | 18 | 2.72 | 0.7 | 24.1 | Faible
182 | KENZA | KENZA AADAM | O2C | Support Bracket kit | OPM | Validated | 2024-05-03 | 2024-09-04 | NC | 2025-09-18 | 2025-10-30 | VAL |  |  | NC |  |  | NC | 2026-02-25 | 2026-02-25 | VAL | 3 | 18 | 2.72 | 0.7 | 24.1 | Faible
183 | KENZA | KENZA AADAM | O2C | Rack bumpers | OPM | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2025-11-24 | 2025-11-24 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
184 | KENZA | KENZA AADAM | L21 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
185 | KENZA | KENZA AADAM | L22 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
186 | KENZA | KENZA AADAM | L23 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
187 | KENZA | KENZA AADAM | L24 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
188 | KENZA | KENZA AADAM | L25 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
189 | KENZA | KENZA AADAM | L26 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
190 | KENZA | KENZA AADAM | L27 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
191 | KENZA | KENZA AADAM | L28 | L21 CEFA - WTB | CEFA | Ongoing |  |  | NC | 2025-12-10 | 2025-12-10 | VAL | 2026-02-25 | 2026-02-25 | VAL | 2026-02-27 | 2026-02-27 | VAL |  |  | NS | 2 | 9.75 | 1.7 | 1 | 15.1 | Très faible
192 | KENZA | KENZA AADAM | CC24 | SMART CAR RETRO JAPAN |  | Validated |  |  | NC |  |  | NC | 2026-03-16 | 2026-03-16 | VAL |  |  | NC |  |  | NC | 4 | 26.42 | 4.48 | 1 | 39.7 | Faible
193 | MSALHA | MERIEM BENHAFID | HX250 | NEW CABIN FLOOR ASSY-Comet | Comet | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
194 | MSALHA | MERIEM BENHAFID | HX250 | CROSSMEMBER ASSY REAR KICK-UP-Comet | Comet | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
195 | MSALHA | MERIEM BENHAFID | HX250 | CROSSMEMBER REAR UNDERFLOOR ASSY / CS TRAV COLL LONG POST-Comet | Comet | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
196 | MSALHA | MERIEM BENHAFID | HX250 | CROSSMEMBER UNDERFLOOR CENTER / CS TRAV COLL LONG7-Comet | Comet | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
197 | MSALHA | MERIEM BENHAFID | HX250 | CROSSMEMBER REAR SEAT MOUNTING-Comet | Comet | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
198 | MSALHA | MERIEM BENHAFID | HX250 | BATTERY FUEL CELL-Symbio | Symbio | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
199 | MSALHA | MERIEM BENHAFID | HX250 | HUMIDIFICATEUR AIR MECATRONIQUE- Symbio | Symbio | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
200 | MSALHA | MERIEM BENHAFID | HX250 | HYDROngoingEN STORAGE SYSTEM | Plastic OMNIUM | Canceled |  |  | NC |  |  | NC |  |  | NC |  |  | NS | 2025-06-13 | 2026-04-14 | NS | 5 | 33.42 | 5.36 | 0.87 | 47.5 | Moyen
201 | MSALHA | MERIEM BENHAFID | F1H | Steering wheel | ZF | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-07-12 | 2025-02-26 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
202 | MSALHA | MERIEM BENHAFID | F1H | Seat Airbag | ZF | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-07-29 | 2025-02-26 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
203 | MSALHA | MERIEM BENHAFID | F1H | Headlamp | VALEO | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-10-29 | 2026-01-20 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
204 | MSALHA | MERIEM BENHAFID | F1H | taillamp | FEKA | Ongoing |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2025-04-16 | 2026-03-30 | Ongoing | 5 | 33.42 | 5.34 | 0.86 | 47.3 | Moyen
205 | MSALHA | MERIEM BENHAFID | F1H | door apliques | NOVARES | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-05-22 | 2026-02-27 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
206 | MSALHA | MERIEM BENHAFID | F1H | tailgate | PRIMA | Ongoing |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2025-04-11 | 2026-03-31 | Ongoing | 5 | 33.42 | 5.34 | 0.86 | 47.3 | Moyen
207 | MSALHA | MERIEM BENHAFID | F1H | headliner | FOMPAK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-10-09 | 2026-02-19 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
208 | MSALHA | MERIEM BENHAFID | F1H | central airvents | ITW | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-18 | 2026-03-04 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
209 | MSALHA | MERIEM BENHAFID | F1H | lateral airvents | ITW | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-18 | 2026-03-25 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
210 | MSALHA | MERIEM BENHAFID | F1H | roof bar | HYDRO | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-08-30 | 2026-03-12 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
211 | MSALHA | MERIEM BENHAFID | F1H | front glasss run chanel | HUTCHINSON | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-07-08 | 2026-03-18 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
212 | MSALHA | MERIEM BENHAFID | F1H | rear glass run channel | HUTCHINSON | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-07-08 | 2026-03-18 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
213 | MSALHA | MERIEM BENHAFID | F1H | front wheel arch trim | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-08-02 | 2026-01-15 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
214 | MSALHA | MERIEM BENHAFID | F1H | rear wheel arch trim | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-08-02 | 2026-01-14 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
215 | MSALHA | MERIEM BENHAFID | F1H | rear wheel trim door | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-08-02 | 2026-01-19 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
216 | MSALHA | MERIEM BENHAFID | F1H | spoiler poster | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-08-02 | 2026-01-20 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
217 | MSALHA | MERIEM BENHAFID | F1H | spoiler nolders | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-08-02 | 2026-01-27 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
218 | MSALHA | MERIEM BENHAFID | F1H | lower aplique | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-08-02 | 2026-03-24 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
219 | MSALHA | MERIEM BENHAFID | F1H | still cladding | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-23 | 2026-01-21 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
220 | MSALHA | MERIEM BENHAFID | F1H | cross car beam | PROMA | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-04-25 | 2026-03-24 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
221 | MSALHA | MERIEM BENHAFID | F1H | 9847519880/9848265680/9865509280/9865509480 | BANT BORU | Ongoing |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2025-01-21 | 2026-04-06 | Ongoing | 5 | 33.42 | 5.31 | 0.85 | 47 | Moyen
222 | MSALHA | MERIEM BENHAFID | F1H MHEV | Exhaust hot end | FORVIA | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-05-16 | 2026-03-11 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
223 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | front ACD damper | MAYSAN MONDO | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-04-08 | Ongoing | 5 | 33.42 | 5.26 | 0.83 | 46.6 | Moyen
224 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | Brake booster | ZF | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-04-08 | Ongoing | 5 | 33.42 | 5.26 | 0.83 | 46.6 | Moyen
225 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | Steering column | NEXTEER | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-03-25 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
226 | MSALHA | MERIEM BENHAFID | F1H | front skid plate | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-10 | 2026-02-10 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
227 | MSALHA | MERIEM BENHAFID | F1H | rear skid plate | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-10 | 2026-02-10 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
228 | MSALHA | MERIEM BENHAFID | F1H | upper grille | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-10 | 2026-02-10 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
229 | MSALHA | MERIEM BENHAFID | F1H | lower grille bezel front | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-10 | 2026-02-10 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
230 | MSALHA | MERIEM BENHAFID | F1H | lower grille bezel closeout | ADPLASTIK | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-09-10 | 2026-02-12 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
231 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | battery housing | MINTH | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-02-12 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
232 | MSALHA | MERIEM BENHAFID | F1H MHEV | Fuel tank | OPMOBILITY | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2025-05-21 | 2026-02-11 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
233 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | Lid traction battery | COMET SUD | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-03-17 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
234 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | Brake pedal RHD | SL | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-02-26 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
235 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | Wiper driver | BOSCH | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-04-08 | Ongoing | 5 | 33.42 | 5.26 | 0.83 | 46.6 | Moyen
236 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | Wiper passenger | BOSCH | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-04-08 | Ongoing | 5 | 33.42 | 5.26 | 0.83 | 46.6 | Moyen
237 | MSALHA | MERIEM BENHAFID | CC21 | SIDE FASCIA REINFORCER RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2024-10-01 | VAL | 2024-10-03 | 2026-03-25 | Ongoing | 4 | 24.92 | 3.87 | 0.8 | 34.3 | Faible
238 | MSALHA | MERIEM BENHAFID | CC21 | Upper bracket RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-10-01 | VAL | 2025-10-03 | 2026-03-24 | Ongoing | 4 | 24.92 | 4.07 | 0.91 | 36.1 | Faible
239 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | Hydro block | BOSCH | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-03-01 | 2026-02-26 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
240 | MSALHA | MERIEM BENHAFID | CC21 | Moustache | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-11-03 | VAL | 2024-10-28 | 2026-03-26 | Ongoing | 4 | 24.92 | 3.88 | 0.8 | 34.3 | Faible
241 | MSALHA | MERIEM BENHAFID | CC21 | FR air dam RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-10-01 | VAL | 2024-10-28 | 2026-03-31 | Ongoing | 4 | 24.92 | 3.88 | 0.8 | 34.3 | Faible
242 | MSALHA | MERIEM BENHAFID | CC21 | FR AIR GUIDE RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-12-03 | VAL | 2025-12-16 | 2026-03-31 | Ongoing | 4 | 24.92 | 4.26 | 1.02 | 37.7 | Faible
243 | MSALHA | MERIEM BENHAFID | CC21 | Color decor RH painted and grained | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-11-03 | VAL | 2024-10-28 | 2026-03-25 | Ongoing | 4 | 24.92 | 3.88 | 0.8 | 34.3 | Faible
244 | MSALHA | MERIEM BENHAFID | CC21 | Fr fOngoinglamp bracket RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-10-01 | VAL | 2025-10-03 | 2026-04-07 | Ongoing | 4 | 24.92 | 4.05 | 0.9 | 35.9 | Faible
245 | MSALHA | MERIEM BENHAFID | CC21 | GRILLE COVER RH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-11-03 | VAL | 2024-10-28 | 2026-03-25 | Ongoing | 4 | 24.92 | 3.88 | 0.8 | 34.3 | Faible
246 | MSALHA | MERIEM BENHAFID | CC21 | LOWER COVER | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-11-03 | VAL | 2024-10-28 | 2026-03-25 | Ongoing | 4 | 24.92 | 3.88 | 0.8 | 34.3 | Faible
247 | MSALHA | MERIEM BENHAFID | CC21 | REAR BUMPER TOW HOOK COVER | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-11-03 | VAL | 2024-10-28 | 2026-03-25 | Ongoing | 4 | 24.92 | 3.88 | 0.8 | 34.3 | Faible
248 | MSALHA | MERIEM BENHAFID | CC21 | REAR BUMPER SIDE BRACKET RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-10-01 | VAL | 2025-10-03 | 2026-03-24 | Ongoing | 4 | 24.92 | 4.07 | 0.91 | 36.1 | Faible
249 | MSALHA | MERIEM BENHAFID | CC21 | RR BUMPER CENTRAL SENSOR BRACKET RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-10-01 | VAL | 2025-10-03 | 2026-03-24 | Ongoing | 4 | 24.92 | 4.07 | 0.91 | 36.1 | Faible
250 | MSALHA | MERIEM BENHAFID | CC21 | RR BUMPER LAT SENSOR BRACKET RH/LH | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-11-03 | VAL | 2024-10-28 | 2026-04-03 | Ongoing | 4 | 24.92 | 3.88 | 0.8 | 34.3 | Faible
251 | MSALHA | MERIEM BENHAFID | CC21 | FR bumper skin | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-04-08 | Ongoing | 4 | 24.92 | 4.05 | 0.9 | 35.9 | Faible
252 | MSALHA | MERIEM BENHAFID | CC21 | FR lower skin | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-04-14 | Ongoing | 4 | 24.92 | 4.04 | 0.9 | 35.8 | Faible
253 | MSALHA | MERIEM BENHAFID | CC21 | FR upper grill | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-04-09 | Ongoing | 4 | 24.92 | 4.05 | 0.9 | 35.8 | Faible
254 | MSALHA | MERIEM BENHAFID | CC21 | RR lower skin | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-04-07 | Ongoing | 4 | 24.92 | 4.05 | 0.9 | 35.9 | Faible
255 | MSALHA | MERIEM BENHAFID | CC21 | FR softnose | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-04-13 | Ongoing | 4 | 24.92 | 4.04 | 0.9 | 35.8 | Faible
256 | MSALHA | MERIEM BENHAFID | CC21 | FR Skidplate | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-04-01 | Ongoing | 4 | 24.92 | 4.06 | 0.91 | 35.9 | Faible
257 | MSALHA | MERIEM BENHAFID | CC21 | FR Deflector | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-03-26 | Ongoing | 4 | 24.92 | 4.07 | 0.91 | 36 | Faible
258 | MSALHA | MERIEM BENHAFID | CC21 | RR bumper skin | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-03-25 | Ongoing | 4 | 24.92 | 4.07 | 0.91 | 36 | Faible
259 | MSALHA | MERIEM BENHAFID | CC21 | RR Skidplate | OPMOBILITY | Ongoing |  |  | NC |  |  | NC |  |  | NC | 2024-07-03 | 2025-04-29 | VAL | 2025-10-03 | 2026-03-27 | Ongoing | 4 | 24.92 | 4.07 | 0.91 | 36 | Faible
260 | MSALHA | MERIEM BENHAFID | F1H | upper c pillar | PRIMA | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2025-01-13 | 2026-01-12 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
261 | MSALHA | MERIEM BENHAFID | F1H | winshield | NSG | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-07-15 | 2026-01-20 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
262 | MSALHA | MERIEM BENHAFID | F1H | front door glass | NSG | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-11-29 | 2026-01-13 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
263 | MSALHA | MERIEM BENHAFID | F1H | rear door glass | NSG | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-07-15 | 2026-01-12 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
264 | MSALHA | MERIEM BENHAFID | F1H | back light | NSG | Validated |  |  | NC |  |  | NC |  |  | NC |  |  | NC | 2024-07-15 | 2026-02-17 | VAL | 4 | 26.17 | 5.2 | 1 | 46 | Moyen
265 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | FRONT ACD DAMPER | KYB | Validated | [11 empty] | NC | 2024-07-15 | 2026-03-12 | VAL | 1 | 8.5 | 1.42 | 1 | 12.5 | Très faible
266 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | E-compressor | MAHLE | Validated | [11 empty] | NC | 2024-07-15 | 2026-03-19 | VAL | 1 | 8.5 | 1.42 | 1 | 12.5 | Très faible
267 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | HVAC | DENSO | Validated | [11 empty] | NC | 2024-07-15 | 2026-03-26 | VAL | 1 | 8.5 | 1.42 | 1 | 12.5 | Très faible
268 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | CROSS FRAME | benteler | Validated | [11 empty] | NC | 2024-07-15 | 2026-03-18 | VAL | 1 | 8.5 | 1.42 | 1 | 12.5 | Très faible
269 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | FLOOR CARPET | AUTONEUM | Validated | [11 empty] | NC | 2024-07-15 | 2026-03-18 | VAL | 1 | 8.5 | 1.42 | 1 | 12.5 | Très faible
270 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | IVI | FAURECIA | Validated | [11 empty] | NC | 2024-07-15 | 2026-03-19 | VAL | 1 | 8.5 | 1.42 | 1 | 12.5 | Très faible
271 | MSALHA | MERIEM BENHAFID | F1H & CC21 C/O | ELECTRIC ENGINE | Nidec | Validated | [11 empty] | NC | 2024-07-15 | 2026-03-18 | VAL | 1 | 8.5 | 1.42 | 1 | 12.5 | Très faible
272 | SKN | SOUKAINA EL OIRDI | CR3 | AIRVENT_FASCIA_COVER_LH_ASSEMBLED | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-23 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 1.99 | 0.37 | 17.6 | Très faible
273 | SKN | SOUKAINA EL OIRDI | CR3 | AIRVENT_FASCIA | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
274 | SKN | SOUKAINA EL OIRDI | CR3 | End cover LH/RH | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
275 | SKN | SOUKAINA EL OIRDI | CR3 | Curtain steering column/GAP HIDER | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
276 | SKN | SOUKAINA EL OIRDI | CR3 | Deco trim Driver | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
277 | SKN | SOUKAINA EL OIRDI | CR3 | Deco trim Passenger SM1004031N | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
278 | SKN | SOUKAINA EL OIRDI | CR3 | Front CC Storage PPEA | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
279 | SKN | SOUKAINA EL OIRDI | CR3 | HUD Cover SM1004031N | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
280 | SKN | SOUKAINA EL OIRDI | CR3 | CC Side panel | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
281 | SKN | SOUKAINA EL OIRDI | CR3 | Top cover IP | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
282 | SKN | SOUKAINA EL OIRDI | CR3 | IP Lower | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
283 | SKN | SOUKAINA EL OIRDI | CR3 | Glove Box | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
284 | SKN | SOUKAINA EL OIRDI | CR3 | DRIVER LOWER ASSEMBLED | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
285 | SKN | SOUKAINA EL OIRDI | CR3 | GRILLE HP ASSEMBLED | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
286 | SKN | SOUKAINA EL OIRDI | CR3 | SUPPORT ECRAN ASSEMBLED | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
287 | SKN | SOUKAINA EL OIRDI | CR3 | SUPPORT INTERRUPTEUR MISTRAL | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
288 | SKN | SOUKAINA EL OIRDI | CR3 | Back cover | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-12-04 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
289 | SKN | SOUKAINA EL OIRDI | CR3 | Shroud Assy | Forvia | Validated | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-07-09 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
290 | SKN | SOUKAINA EL OIRDI | CR3 | TAILGATE | PO |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-09-25 | 2026-05-30 | Ongoing | 5 | 33.42 | 2.18 | 0.35 | 19.3 | Très faible
291 | SKN | SOUKAINA EL OIRDI | CR3 | STEERING COLUMN ASS WO CAMERA without | SMRC |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-07-09 | 2026-04-03 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
292 | SKN | SOUKAINA EL OIRDI | CR3 | SUNROOF | WEBASTO |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-02-26 | 2026-03-06 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
293 | SKN | SOUKAINA EL OIRDI | CR3 | HEADLINER NR | ADLER |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-09-03 | 2026-06-27 | Ongoing | 5 | 33.42 | 2.27 | 0.39 | 20.1 | Faible
294 | SKN | SOUKAINA EL OIRDI | CR3 | HEADLINER SR | ADLER |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-09-03 | 2026-06-27 | Ongoing | 5 | 33.42 | 2.27 | 0.39 | 20.1 | Faible
295 | SKN | SOUKAINA EL OIRDI | CR3 | WINDSHIELD | SGS |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-11-27 | 2025-11-17 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
296 | SKN | SOUKAINA EL OIRDI | CR3 | REAR DOOR GLASS/ vitre porte AR | NSG |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-09-10 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
297 | SKN | SOUKAINA EL OIRDI | CR3 | REAR QUARTER GLASS/ VITRE Custode | NSG |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-07-01 | 2025-01-19 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
298 | SKN | SOUKAINA EL OIRDI | CR3 | Backlite /VITRE VOLET | NSG |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-09-10 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
299 | SKN | SOUKAINA EL OIRDI | CR3 | FLOOR CARPET | ADLER |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-02-12 | 2026-06-05 | Ongoing | 5 | 33.42 | 2.21 | 0.36 | 19.5 | Très faible
300 | SKN | SOUKAINA EL OIRDI | CR3 | DASH INSULATOR | ADLER |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-03-19 | 2026-06-06 | Ongoing | 5 | 33.42 | 2.21 | 0.37 | 19.6 | Très faible
301 | SKN | SOUKAINA EL OIRDI | CR3 | DOOR TRIM PANEL -front/AV | EUROSTYLE |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-03-12 | 2025-11-17 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
302 | SKN | SOUKAINA EL OIRDI | CR3 | DOOR TRIM PANEL rear/AR | EUROSTYLE |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-03-12 | 2025-11-17 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
303 | SKN | SOUKAINA EL OIRDI | CR3 | Front/ AV door window switch bezel LH/RH | EUROSTYLE |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-06-04 | 2025-01-17 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
304 | SKN | SOUKAINA EL OIRDI | CR3 | Rear/AR door window switch bezel LH/RH | EUROSTYLE |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-06-04 | 2025-11-20 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
305 | SKN | SOUKAINA EL OIRDI | CR3 | Gousset AV/AR D/G | EUROSTYLE |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-06-04 | 2025-11-20 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
306 | SKN | SOUKAINA EL OIRDI | CR3 | Front Embellisher | Zanini |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-06-04 | 2025-11-28 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
307 | SKN | SOUKAINA EL OIRDI | CR3 | CROSS CAR BEAM | Benteler |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-03-19 | 2026-02-14 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
308 | SKN | SOUKAINA EL OIRDI | CR3 | EXTERNAL MIRROR FG | SMR |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-11-26 | 2025-12-05 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
309 | SKN | SOUKAINA EL OIRDI | CR3 | REAR CONSOLE | SIGIT |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-01-29 | 2025-12-25 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
310 | SKN | SOUKAINA EL OIRDI | STLAM | AMPLIFICATEUR MAITRE CYLINDRE TANDEM | ZF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-03-27 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
311 | SKN | SOUKAINA EL OIRDI | STLAM | AMORTISSEUR AR CONVENTIONNEL-DRIV | DRIV |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-03-11 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
312 | SKN | SOUKAINA EL OIRDI | STLAM | AMORTISSEUR AVANT CONVENTIONNEL-DRIV | DRIV |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-03-17 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
313 | SKN | SOUKAINA EL OIRDI | STLAM | BARRE ANTI DEVERS AVANT-SOngoingEFI | SOngoingEFI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-04-20 | Ongoing | 5 | 33.42 | 2.17 | 0.35 | 19.2 | Très faible
314 | SKN | SOUKAINA EL OIRDI | STLAM | COLONNE DE DIRECTION-BOSCH | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-05-12 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
315 | SKN | SOUKAINA EL OIRDI | STLAM | CONDENSEUR EAU CIRCUIT AERO ENS - PAC-VALEO | VALEO |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-01-12 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
316 | SKN | SOUKAINA EL OIRDI | STLAM | E-BOOSTER (amplificateur maitre cylindre tandem)-BOSCH | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-05-30 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
317 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER ARRIERE MOTORISE 290x12 Ø42 | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-05-06 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
318 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER ARRIERE MOTORISE 330x14 Ø45 | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-04-22 | Ongoing | 5 | 33.42 | 2.17 | 0.35 | 19.2 | Très faible
319 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER ARRIERE MOTORISE 356x26 Ø45/48 | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-05-09 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
320 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER ARRIERE MOTORISE 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-29 | Ongoing | 2024-04-15 | 2026-06-26 | Ongoing | 5 | 33.42 | 1.61 | 0.27 | 14.3 | Très faible
321 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-24 | Ongoing | 2026-04-24 | 2026-06-30 | NS | 5 | 33.42 | 2.31 | 0.57 | 20.5 | Faible
322 | SKN | SOUKAINA EL OIRDI | STLAM | GROUPE CLIMATISATION-DENSO | DENSO |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-02-18 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
323 | SKN | SOUKAINA EL OIRDI | STLAM | REDUCTEUR AWD-GKN | GKN |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-03-09 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
324 | SKN | SOUKAINA EL OIRDI | STLAM | TUBE RACCORD 2 VOIES D/G (tuyau frein) -TI FS | TI FS |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-03-08 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
325 | SKN | SOUKAINA EL OIRDI | STLAM | DAE MECANISME DE DIRECTION-JTEkt | JTEkt |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-04-06 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
326 | SKN | SOUKAINA EL OIRDI | STLAM | ARTICULATION TRIANGLE E2-Hutchinson | Hutchinson |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-05-02 | Ongoing | 2026-05-02 | 2027-10-14 | NS | 5 | 33.42 | 1.65 | 0.28 | 14.6 | Très faible
327 | SKN | SOUKAINA EL OIRDI | STLAM | BIELLETTE TAR MB-Hutchinson | Hutchinson |  | 2024-01-04 | 2024-07-17 | NC | 2025-05-12 | 2025-11-22 | VAL | 2025-11-13 | 2026-01-28 | VAL | 2026-01-28 | 2026-06-02 | Ongoing | 2026-06-02 | 2027-10-14 | NS | 3 | 18.25 | 0.67 | 0.21 | 5.9 | Très faible
328 | SKN | SOUKAINA EL OIRDI | J4U | ERAD 3 - J4U | ZF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-12-12 | VAL | 2025-12-12 | 2026-04-17 | NS | 4 | 24.92 | 1.83 | 0.5 | 16.2 | Très faible
329 | SKN | SOUKAINA EL OIRDI | STLAM | Amortisseur AR DBH CR3 -KYBEH | KYBEH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-12-24 | VAL | 2025-06-23 | 2026-05-20 | Ongoing | 4 | 24.92 | 1.58 | 0.36 | 14 | Très faible
330 | SKN | SOUKAINA EL OIRDI | STLAM | Amortisseur AV DBH CR3 -KYBEH | KYBEH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-12-24 | VAL | 2025-06-23 | 2026-04-25 | Ongoing | 4 | 24.92 | 1.59 | 0.37 | 14.1 | Très faible
331 | SKN | SOUKAINA EL OIRDI | J4U | Traverse Multibras J4U | Marelli |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | VAL | 2024-11-01 | 2026-06-15 | Ongoing | 4 | 24.92 | 1.51 | 0.32 | 13.4 | Très faible
332 | SKN | SOUKAINA EL OIRDI | STLAM | Cooling plate PHEV STLA M | Humrey |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-02-05 | 2026-02-18 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
333 | SKN | SOUKAINA EL OIRDI | STLAM | Cooling plate BEV STLA M | Humrey |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-02-05 | 2026-02-18 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
334 | SKN | SOUKAINA EL OIRDI | J4U | Cooling plate PHEV STLA M | HBR |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-04-17 | NS | 5 | 33.42 | 2.24 | 0.38 | 19.8 | Très faible
335 | SKN | SOUKAINA EL OIRDI | J4U | Cooling plate BEV STLA M | HBR |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-04-17 | NS | 5 | 33.42 | 2.24 | 0.38 | 19.8 | Très faible
336 | SKN | SOUKAINA EL OIRDI | J4U | IP CCB | Tiberina |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-01-22 | 2026-05-30 | Ongoing | 5 | 33.42 | 2.2 | 0.36 | 19.5 | Très faible
337 | SKN | SOUKAINA EL OIRDI | J4U | réservoirs carb - PHEV fuel tank | Yapp |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-12-05 | VAL | 2025-08-27 | 2026-05-12 | Ongoing | 4 | 24.92 | 1.62 | 0.38 | 14.3 | Très faible
338 | SKN | SOUKAINA EL OIRDI | J4U | réservoirs carb - MHEV fuel tank | Yapp |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-12-05 | VAL | 2025-08-27 | 2026-05-23 | Ongoing | 4 | 24.92 | 1.61 | 0.38 | 14.3 | Très faible
339 | SKN | SOUKAINA EL OIRDI | J4U | DAE MECANISME DE DIRECTION-JTEkt | JTEkt |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-10-22 | 2026-03-24 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
340 | SKN | SOUKAINA EL OIRDI | J4U | Exhaust LINE PHEV | Forvia |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC |  | 2026-06-27 | Ongoing | 5 | 33.42 | 2.55 | 0.51 | 22.6 | Faible
341 | SKN | SOUKAINA EL OIRDI | J4U | Exhaust LINE MHEV | Forvia |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2025-07-14 | 2026-05-27 | Ongoing | 5 | 33.42 | 2.26 | 0.39 | 20 | Faible
342 | SKN | SOUKAINA EL OIRDI | STLAM | AMPLIFICATEUR MAITRE CYLINDRE TANDEM -Melfi | ZF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-15 | 2026-05-23 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
343 | SKN | SOUKAINA EL OIRDI | STLAM | BARRE ANTI DEVERS AVANT-SOngoingEFI-CR3 | SOngoingEFI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-16 | 2026-03-01 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
344 | SKN | SOUKAINA EL OIRDI | STLAM | BARRE ANTI DEVERS AVANT-SOngoingEFI-MELFI | SOngoingEFI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-17 | 2026-04-30 | Ongoing | 5 | 33.42 | 2.17 | 0.35 | 19.2 | Très faible
345 | SKN | SOUKAINA EL OIRDI | STLAM | COLONNE DE DIRECTION-BOSCH-SX | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-18 | 2026-03-13 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
346 | SKN | SOUKAINA EL OIRDI | STLAM | COLONNE DE DIRECTION-BOSCH-Melfi | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-19 | 2026-05-30 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
347 | SKN | SOUKAINA EL OIRDI | STLAM | CONDENSEUR EAU CIRCUIT AERO ENS - PAC-VALEO -Melfi | VALEO |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-22 | 2026-06-16 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
348 | SKN | SOUKAINA EL OIRDI | STLAM | E-BOOSTER (amplificateur maitre cylindre tandem)-BOSCH-ESH | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-23 | 2026-05-11 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
349 | SKN | SOUKAINA EL OIRDI | STLAM | E-BOOSTER (amplificateur maitre cylindre tandem)-BOSCH-RJ | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-24 | 2026-05-30 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
350 | SKN | SOUKAINA EL OIRDI | STLAM | E-BOOSTER (amplificateur maitre cylindre tandem)-BOSCH-Melfi | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-25 | 2026-06-26 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.1 | Très faible
351 | SKN | SOUKAINA EL OIRDI | STLAM | E-BOOSTER (amplificateur maitre cylindre tandem)-BOSCH-Melfi | BOSCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-26 | 2026-07-14 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.1 | Très faible
352 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 365x37 2xØ44 -MELFI | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-27 | 2026-06-10 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
353 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 365x37 2xØ44-RJ | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-28 | 2026-04-22 | Ongoing | 5 | 33.42 | 2.17 | 0.35 | 19.2 | Très faible
354 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 365x37 2xØ44-MElfi | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-29 | 2026-04-22 | Ongoing | 5 | 33.42 | 2.17 | 0.35 | 19.2 | Très faible
355 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 365x37 2xØ44-MElfi | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-04-30 | 2026-06-10 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
356 | SKN | SOUKAINA EL OIRDI | STLAM | GROUPE CLIMATISATION-DENSO -RJ | DENSO |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-01 | 2026-03-25 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
357 | SKN | SOUKAINA EL OIRDI | STLAM | GROUPE CLIMATISATION-DENSO - Melfi | DENSO |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-02 | 2026-05-30 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
358 | SKN | SOUKAINA EL OIRDI | STLAM | REDUCTEUR AWD-GKN - Melfi | GKN |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-03 | 2026-06-10 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
359 | SKN | SOUKAINA EL OIRDI | STLAM | REDUCTEUR AWD-GKN - RJ | GKN |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-04 | 2026-06-24 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
360 | SKN | SOUKAINA EL OIRDI | STLAM | REDUCTEUR AWD-GKN - Melfi | GKN |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-05 | 2026-06-27 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
361 | SKN | SOUKAINA EL OIRDI | STLAM | REDUCTEUR AWD-GKN - Melfi | GKN |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-06 | 2026-06-24 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
362 | SKN | SOUKAINA EL OIRDI | STLAM | SUPPORT CHARGEUR BEV - Melfi | savreux |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-09 | 2026-06-20 | Ongoing | 5 | 33.42 | 2.16 | 0.34 | 19.2 | Très faible
363 | SKN | SOUKAINA EL OIRDI | STLAM | DAE MECANISME DE DIRECTION-JTEkt -RJ | JTEkt |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-10 | 2026-03-25 | VAL | 4 | 26.17 | 2.1 | 0.39 | 18.6 | Très faible
364 | SKN | SOUKAINA EL OIRDI | STLAM | DAE MECANISME DE DIRECTION-JTEkt -Melfi | JTEkt |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-11 | 2026-05-29 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
365 | SKN | SOUKAINA EL OIRDI | STLAM | IP CCB - Melfi | Tiberina |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-12 | 2026-06-12 | NS | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
366 | SKN | SOUKAINA EL OIRDI | STLAM | réservoirs carb - PHEV fuel tank -Melfi | Yapp |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-13 | 2026-06-13 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
367 | SKN | SOUKAINA EL OIRDI | STLAM | réservoirs carb - MHEV fuel tank - Melfi | Yapp |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-14 | 2026-06-14 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
368 | SKN | SOUKAINA EL OIRDI | STLAM | Exhaust LINE PHEV - Melfi | Forvia |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-15 | 2026-06-10 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
369 | SKN | SOUKAINA EL OIRDI | STLAM | Exhaust LINE MHEV -Melfi | Forvia |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2025-04-20 | NC | 2024-05-16 | 2026-06-01 | Ongoing | 5 | 33.42 | 2.17 | 0.34 | 19.2 | Très faible
370 | SKN | SOUKAINA EL OIRDI | B10 | BAR ANTIROLL FRT meili | meili | Ongoing |  |  | NC | 2026-01-23 | 2026-01-26 | VAL | 2026-01-26 | 2026-04-06 | NC |  | 2026-06-24 | NC |  | 2026-09-16 | NC | 4 | 25.25 | 3.82 | 0.9 | 33.8 | Faible
371 | SKN | SOUKAINA EL OIRDI | B10 | FRONT END MODULE -FEM- BTZ | BATZ | Ongoing |  |  | NC | 2026-01-22 | 2026-02-13 | VAL | 2026-02-13 | 2026-04-24 | VAL | 2026-03-27 | 2026-07-03 | NS |  | 2026-09-25 | NS | 3 | 18.25 | 2.31 | 0.81 | 20.5 | Faible
372 | SKN | SOUKAINA EL OIRDI | B10 | FRT SUSPENSION MODULE LH / RH | CIJAN | Ongoing |  |  | NC | 2026-01-08 | 2026-01-08 | VAL | 2026-01-08 | 2026-04-29 | VAL | 2026-03-27 | 2026-07-22 | NS |  | 2026-10-14 | NS | 3 | 18.25 | 2.21 | 0.79 | 19.6 | Très faible
373 | SKN | SOUKAINA EL OIRDI | B10 | STRUT ASSY RR LH / RH | CIJAN | Ongoing |  |  | NC | 2026-01-08 | 2026-01-12 | VAL | 2026-01-12 | 2026-04-29 | Ongoing |  | 2026-07-22 | NS |  | 2026-10-14 | NS | 4 | 25.25 | 3.58 | 0.85 | 31.7 | Faible
374 | SKN | SOUKAINA EL OIRDI | B10 | RR FLEXIBLE - LH RR BAIL TUBE | TIFS | Ongoing |  |  |  | 2026-01-09 | 2026-01-28 | VAL | 2026-01-28 | 2026-04-08 | Ongoing |  | 2026-07-01 | NS |  | 2026-09-23 | NS | 3 | 22.75 | 2.57 | 0.87 | 22.7 | Faible
375 | SKN | SOUKAINA EL OIRDI | B10 | RR HOSE - RH RR CALIPER PIPE | TIFS | Ongoing |  |  |  | 2026-01-09 | 2026-01-28 | VAL | 2026-01-28 | 2026-04-08 | Ongoing |  | 2026-07-01 | NS |  | 2026-09-23 | NS | 3 | 22.75 | 2.57 | 0.87 | 22.7 | Faible
376 | SKN | SOUKAINA EL OIRDI | B10 | SPOILER | IAC | Ongoing |  |  |  | 2026-01-27 | 2026-03-27 | Ongoing |  | 2026-05-29 | NS |  | 2026-08-07 | NS |  | 2026-10-30 | NS | 4 | 30.92 | 4.01 | 0.93 | 35.5 | Faible
377 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER ARRIERE MOTORISE 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-29 | Ongoing | 2024-04-15 | 2026-07-07 | Ongoing | 5 | 33.42 | 1.61 | 0.27 | 14.3 | Très faible
378 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER ARRIERE MOTORISE 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-29 | Ongoing | 2024-04-15 | 2026-06-23 | Ongoing | 5 | 33.42 | 1.62 | 0.27 | 14.3 | Très faible
379 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER ARRIERE MOTORISE 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-29 | Ongoing | 2024-04-15 | 2026-06-18 | Ongoing | 5 | 33.42 | 1.62 | 0.27 | 14.3 | Très faible
380 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-24 | Ongoing | 2026-04-24 | 2026-07-03 | NS | 5 | 33.42 | 2.28 | 0.56 | 20.2 | Faible
381 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-24 | Ongoing | 2026-04-24 | 2026-06-23 | NS | 5 | 33.42 | 2.4 | 0.61 | 21.2 | Faible
382 | SKN | SOUKAINA EL OIRDI | STLAM | ETRIER AVANT & PLAQUETTES 340 - downsizing | HITACHI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2024-09-15 | 2025-01-22 | NC | 2025-01-22 | 2026-04-24 | Ongoing | 2026-04-24 | 2026-07-23 | NS | 5 | 33.42 | 2.12 | 0.49 | 18.7 | Très faible
383 | SKN | SOUKAINA EL OIRDI | F1H | 9853179480 | AGRATI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-24 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
384 | SKN | SOUKAINA EL OIRDI | F1H | 9677460380 | AGRATI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-25 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
385 | SKN | SOUKAINA EL OIRDI | F1H | 6700345050 | AGRATI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-26 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
386 | SKN | SOUKAINA EL OIRDI | F1H | 9864954780 | AGRATI |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-27 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
387 | SKN | SOUKAINA EL OIRDI | F1H | 9800093680 | ADHEX |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-28 | NC | 5 | 33.42 | 2.29 | 0.38 | 20.2 | Faible
388 | SKN | SOUKAINA EL OIRDI | F1H | 9675035780 | ADHEX |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-29 | NC | 5 | 33.42 | 2.29 | 0.38 | 20.2 | Faible
389 | SKN | SOUKAINA EL OIRDI | F1H | 9848091680 | ADHEX |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-30 | NC | 5 | 33.42 | 2.29 | 0.38 | 20.2 | Faible
390 | SKN | SOUKAINA EL OIRDI | F1H | 9827752680 | ADHEX |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-07-31 | NC | 5 | 33.42 | 2.29 | 0.38 | 20.2 | Faible
391 | SKN | SOUKAINA EL OIRDI | F1H | 9859219380 | ADHEX |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-01 | NC | 5 | 33.42 | 2.29 | 0.38 | 20.2 | Faible
392 | SKN | SOUKAINA EL OIRDI | F1H | 9855928380 | HUTCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-02 | NC | 5 | 33.42 | 2.29 | 0.38 | 20.2 | Faible
393 | SKN | SOUKAINA EL OIRDI | F1H | 9855928080 | HUTCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-03 | NC | 5 | 33.42 | 2.28 | 0.38 | 20.2 | Faible
394 | SKN | SOUKAINA EL OIRDI | F1H | 9855927880 | HUTCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-04 | NC | 5 | 33.42 | 2.28 | 0.38 | 20.2 | Faible
395 | SKN | SOUKAINA EL OIRDI | F1H | 9855928180 | HUTCH |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-03-28 | Ongoing | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-05 | NC | 5 | 33.42 | 2.28 | 0.38 | 20.2 | Faible
396 | SKN | SOUKAINA EL OIRDI | F1H | 9867727880 | KIRCHHOFF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-06 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
397 | SKN | SOUKAINA EL OIRDI | F1H | 9839069780 | KIRCHHOFF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-07 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
398 | SKN | SOUKAINA EL OIRDI | F1H | 9866597280 | KIRCHHOFF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-08 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
399 | SKN | SOUKAINA EL OIRDI | F1H | 9841420280 | KIRCHHOFF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-09 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
400 | SKN | SOUKAINA EL OIRDI | F1H | 9839814880 | KIRCHHOFF |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-10 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
401 | SKN | SOUKAINA EL OIRDI | F1H | 9830832080 | ARAYMOND |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-11 | NC | 4 | 26.42 | 1.83 | 0.37 | 16.2 | Très faible
402 | SKN | SOUKAINA EL OIRDI | F1H | 9636940780 | ARAYMOND |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-12 | NC | 4 | 26.42 | 1.82 | 0.37 | 16.2 | Très faible
403 | SKN | SOUKAINA EL OIRDI | F1H | 9846708180 | ARAYMOND |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-13 | NC | 4 | 26.42 | 1.82 | 0.37 | 16.2 | Très faible
404 | SKN | SOUKAINA EL OIRDI | F1H | 9675689580 | ARAYMOND |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-14 | NC | 4 | 26.42 | 1.82 | 0.37 | 16.2 | Très faible
405 | SKN | SOUKAINA EL OIRDI | F1H | 9621824880 | ARAYMOND |  | 2024-01-04 | 2024-07-17 | NC | 2024-07-17 | 2024-09-15 | NC | 2025-12-11 | 2026-02-27 | VAL | 2025-01-22 | 2025-04-20 | NC | 2025-04-20 | 2026-08-15 | NC | 4 | 26.42 | 1.82 | 0.37 | 16.1 | Très faible
406 | SKN | SOUKAINA EL OIRDI | STLAM | ONE BOX | bosch |  |  |  |  | 2026-02-24 | 2026-03-24 | Ongoing | 2026-03-24 | 2026-05-27 | NS | 2026-05-27 | 2027-09-09 | NS | 2027-09-09 | 2027-01-11 | NS | 4 | 30.92 | 3.39 | 0.81 | 30 | Faible
407 | AMR | Amr Arid | FXU | HEADLAMP RH/lh | OPMOBILITY | Ongoing | 2023-02-11 | 2025-09-24 | VAL | 2025-09-25 | 2025-06-11 | NC | 2025-06-11 | 2025-04-12 | NC | 2025-04-12 | 2025-08-27 | VAL | 2025-05-05 | 2026-05-26 | Ongoing | 3 | 22.42 | 2.66 | 0.76 | 23.5 | Faible
408 | AMR | Amr Arid | FXU | center bar light | OPMOBILITY |  | 2023-03-11 | 2025-09-24 | VAL | 2025-09-25 | 2025-06-11 | NC | 2025-06-11 | 2025-04-12 | NC | 2025-04-12 | 2025-08-27 | VAL | 2025-05-05 | 2026-05-27 | Ongoing | 3 | 22.42 | 2.66 | 0.76 | 23.5 | Faible
409 | AMR | Amr Arid | FXU | tail lamp center | OPMOBILITY |  | 2023-03-11 | 2023-08-12 | NC | 2023-08-12 | 2024-01-19 | NC | 2024-01-19 | 2024-02-16 | NC | 2024-02-16 | 2025-08-27 | VAL | 2025-07-21 | 2026-05-28 | Ongoing | 4 | 24.92 | 2.38 | 0.55 | 21.1 | Faible
410 | AMR | Amr Arid | FXU | tail lamp RR LT | OMMOBILITY |  | 2023-02-11 | 2023-07-12 | NC | 2023-07-12 | 2024-01-18 | NC | 2024-01-18 | 2024-02-15 | NC | 2024-02-15 | 2025-08-27 | VAL | 2025-07-21 | 2026-05-29 | Ongoing | 4 | 24.92 | 2.33 | 0.54 | 20.6 | Faible
411 | AMR | Amr Arid | FXU | BACKLITE FX | AGC |  | 2023-02-12 | 2024-06-01 | NC | 2024-06-01 | 2024-02-17 | NC | 2024-02-17 | 2024-03-16 | NC | 2024-03-16 | 2025-07-18 | VAL | 2025-07-23 | 2026-05-30 | Ongoing | 4 | 24.92 | 3.31 | 0.72 | 29.3 | Faible
412 | AMR | Amr Arid | FXU | BACKLITE FU | AGC |  | 2023-02-12 | 2024-06-01 | NC | 2024-06-01 | 2024-02-17 | NC | 2024-02-17 | 2024-03-16 | NC | 2024-03-16 | 2025-07-18 | VAL | 2025-07-23 | 2026-05-31 | Ongoing | 4 | 24.92 | 3.31 | 0.72 | 29.3 | Faible
413 | AMR | Amr Arid | FXU | FLOOR CARP BEV MHEV | TREROC |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2025-07-18 | VAL | 2025-07-23 | 2026-06-01 | Ongoing | 4 | 24.92 | 4.52 | 0.96 | 40 | Moyen
414 | AMR | Amr Arid | FXU | Innerdush | TREROC |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2026-02-15 | 2026-03-15 | VAL | 2026-03-15 | 2026-06-02 | Ongoing | 4 | 24.92 | 5 | 1.23 | 44.3 | Moyen
415 | AMR | Amr Arid | FXU | HEADLINER FX | antolin |  | 2024-02-01 | 2024-06-02 | NC | 2024-06-02 | 2024-03-19 | NC | 2024-03-19 | 2024-04-16 | NC | 2024-04-16 | 2025-09-19 | VAL | 2025-09-17 | 2026-06-03 | Ongoing | 4 | 24.92 | 3.45 | 0.76 | 30.6 | Faible
416 | AMR | Amr Arid | FXU | HEADLINER FU | antolin |  | 2024-02-01 | 2024-06-02 | NC | 2024-06-02 | 2024-03-19 | NC | 2024-03-19 | 2024-04-16 | NC | 2024-04-16 | 2025-10-23 | VAL | 2025-02-10 | 2026-06-16 | Ongoing | 4 | 24.92 | 3.36 | 0.71 | 29.7 | Faible
417 | AMR | Amr Arid | FXU | door panel right | simoldes |  | 2023-02-12 | 2024-06-01 | NC | 2024-06-01 | 2024-02-17 | NC | 2024-02-17 | 2024-03-16 | NC | 2024-03-16 | 2024-04-13 | NC | 2024-04-13 | 2026-05-04 | Ongoing | 5 | 33.42 | 5.34 | 0.84 | 47.3 | Moyen
418 | AMR | Amr Arid | FXU | door panel left | simoldes |  | 2023-02-12 | 2024-06-01 | NC | 2024-06-01 | 2024-02-17 | NC | 2024-02-17 | 2024-03-16 | NC | 2024-03-16 | 2024-04-13 | NC | 2024-04-13 | 2026-06-26 | Ongoing | 5 | 33.42 | 5.34 | 0.83 | 47.2 | Moyen
419 | AMR | Amr Arid | FXU | mirror side bezel | simoldes |  | 2023-02-12 | 2024-06-01 | NC | 2024-06-01 | 2024-02-17 | NC | 2024-02-17 | 2024-03-16 | NC | 2024-03-16 | 2024-04-13 | NC | 2024-04-13 | 2026-06-26 | Ongoing | 5 | 33.42 | 5.34 | 0.83 | 47.2 | Moyen
420 | AMR | Amr Arid | FXU | fRONT SUBFRAMRE | BENTLER |  | 2024-02-04 | 2024-07-05 | NC | 2024-07-05 | 2024-06-18 | NC | 2024-06-18 | 2024-07-16 | NC | 2024-07-16 | 2025-11-07 | VAL | 2025-10-10 | 2026-06-26 | Ongoing | 4 | 24.92 | 3.42 | 0.76 | 30.3 | Faible
421 | AMR | Amr Arid | FXU | FRONT CONTROL ARM | BENTLER |  | 2024-02-04 | 2024-07-05 | NC | 2024-07-05 | 2024-06-18 | NC | 2024-06-18 | 2024-07-16 | NC | 2024-07-16 | 2025-10-31 | VAL | 2025-10-10 | 2026-06-26 | Ongoing | 4 | 24.92 | 3.42 | 0.76 | 30.3 | Faible
422 | AMR | Amr Arid | FXU | RTB | BENTLER |  | 2024-10-04 | 2024-05-15 | NC | 2024-05-15 | 2024-06-26 | NC | 2024-06-26 | 2024-07-24 | NC | 2024-07-24 | 2025-02-10 | VAL | 2025-09-25 | 2026-06-26 | Ongoing | 4 | 24.92 | 4.55 | 0.98 | 40.3 | Moyen
423 | AMR | Amr Arid | FXU | Front glass run seal | hutchinson |  | 2024-02-05 | 2024-06-06 | NC | 2024-06-06 | 2024-07-18 | NC | 2024-07-18 | 2024-08-15 | NC | 2024-08-15 | 2025-06-25 | VAL | 2025-02-10 | 2026-06-26 | Ongoing | 4 | 24.92 | 3.36 | 0.71 | 29.7 | Faible
424 | AMR | Amr Arid | FXU | rear glass run seal | hutchinson |  | 2024-02-05 | 2024-06-06 | NC | 2024-06-06 | 2024-07-18 | NC | 2024-07-18 | 2024-08-15 | NC | 2024-08-15 | 2025-12-14 | VAL | 2025-10-10 | 2026-06-26 | Ongoing | 4 | 24.92 | 3.45 | 0.76 | 30.6 | Faible
425 | AMR | Amr Arid | FXU | EFU BEV 400 | JE |  | 2024-02-05 | 2024-06-06 | NC | 2024-06-06 | 2024-07-18 | NC | 2024-07-18 | 2024-08-15 | NC | 2024-08-15 | 2025-11-14 | VAL | 2025-10-10 | 2026-06-26 | Ongoing | 4 | 24.92 | 3.45 | 0.76 | 30.6 | Faible
426 | AMR | Amr Arid | FXU | FRONT B PILLER | MAIER |  | 2024-12-03 | 2024-04-16 | NC | 2024-04-16 | 2024-05-28 | NC | 2024-05-28 | 2024-06-25 | NC | 2024-06-25 | 2025-11-21 | VAL | 2025-10-15 | 2026-06-26 | Ongoing | 4 | 24.92 | 4.56 | 0.99 | 40.4 | Moyen
427 | AMR | Amr Arid | FXU | REAR B PILLAR | MAIER |  | 2024-12-03 | 2024-04-16 | NC | 2024-04-16 | 2024-05-28 | NC | 2024-05-28 | 2024-06-25 | NC | 2024-06-25 | 2025-11-21 | VAL | 2025-10-15 | 2026-05-11 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
428 | AMR | Amr Arid | FXU | TUYAU ALIMENTATION CARBURANT ASS | SUMIRKO |  | 2025-09-16 | 2025-10-21 | VAL | 2025-08-07 | 2025-08-19 | NC | 2025-08-19 | 2025-09-16 | NC | 2025-09-16 | 2026-05-01 | Ongoing | 2025-10-10 | 2026-06-09 | NS | 4 | 30.92 | 6.99 | 1.41 | 61.9 | Fort
429 | AMR | Amr Arid | FXU | CONSOLE_ENS_WITH_USB/CONSOLE_ENS_WITHOUT_USB | SIGIT |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-01-29 | VAL | 2025-10-11 | 2026-06-23 | Ongoing | 4 | 24.92 | 4.56 | 0.98 | 40.4 | Moyen
430 | AMR | Amr Arid | FXU | FRONT_SIDE_COVERS | SIGIT |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-01-29 | VAL | 2025-10-11 | 2026-06-17 | Ongoing | 4 | 24.92 | 4.57 | 0.99 | 40.4 | Moyen
431 | AMR | Amr Arid | FXU | VIDE-POCHES_AV_CONSOLE | SIGIT |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-01-29 | VAL | 2025-10-11 | 2026-06-17 | Ongoing | 4 | 24.92 | 4.57 | 0.99 | 40.4 | Moyen
432 | AMR | Amr Arid | FXU | REAR COVER_WITH_USB_F2X | SIGIT |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-01-29 | VAL | 2025-10-11 | 2026-05-29 | Ongoing | 4 | 24.92 | 4.58 | 1 | 40.6 | Moyen
433 | AMR | Amr Arid | FXU | ENJOLIVEUR_DESSUS_CONSOLE | SIGIT |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-01-29 | VAL | 2025-10-11 | 2026-05-12 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
434 | AMR | Amr Arid | FXU | C PILLAR UPPER LH/RH F2X | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-02-12 | VAL | 2025-10-11 | 2026-06-10 | Ongoing | 4 | 24.92 | 4.57 | 0.99 | 40.5 | Moyen
435 | AMR | Amr Arid | FXU | LT A Pillar / A Pillar RT | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-02-12 | VAL | 2025-10-11 | 2026-06-16 | Ongoing | 4 | 24.92 | 4.57 | 0.99 | 40.4 | Moyen
436 | AMR | Amr Arid | FXU | REAR SCUFF LH/RH F2X/F2U | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-02-12 | VAL | 2025-10-11 | 2026-06-16 | Ongoing | 4 | 24.92 | 4.57 | 0.99 | 40.4 | Moyen
437 | AMR | Amr Arid | FXU | Lower B Pillar BEVF2X/F2U | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-02-12 | VAL | 2025-10-11 | 2026-06-16 | Ongoing | 4 | 24.92 | 4.57 | 0.99 | 40.4 | Moyen
438 | AMR | Amr Arid | FXU | COWL GRILL LEFT RHD/LHD ASSY FXU | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2025-10-10 | VAL | 2025-10-11 | 2026-06-16 | Ongoing | 4 | 24.92 | 4.57 | 0.99 | 40.4 | Moyen
439 | AMR | Amr Arid | FXU | LOAD FLOOR SUPPORT LH/RH F2X | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-02-12 | VAL | 2025-10-11 | 2026-05-29 | Ongoing | 4 | 24.92 | 4.58 | 1 | 40.6 | Moyen
440 | AMR | Amr Arid | FXU | cowl grill LH LHD ASSY FXU | metaplast |  | 2024-02-13 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2025-05-27 | 2025-10-10 | VAL | 2025-10-11 | 2026-05-29 | Ongoing | 4 | 24.92 | 3.85 | 0.85 | 34.1 | Faible
441 | AMR | Amr Arid | FXU | FRONT SCUFF LH/RH F2X | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-02-12 | VAL | 2025-10-11 | 2026-05-29 | Ongoing | 4 | 24.92 | 4.58 | 1 | 40.6 | Moyen
442 | AMR | Amr Arid | FXU | LATERAL FINISHER RIGHT LEFT | metaplast |  | 2024-02-13 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2025-05-27 | 2025-10-10 | VAL | 2025-11-11 | 2026-05-24 | Ongoing | 4 | 24.92 | 3.89 | 0.87 | 34.4 | Faible
443 | AMR | Amr Arid | FXU | Upper B Pillar | metaplast |  | 2024-12-02 | 2024-03-18 | NC | 2024-03-18 | 2024-04-29 | NC | 2024-04-29 | 2024-05-27 | NC | 2024-05-27 | 2026-02-12 | VAL | 2025-10-11 | 2026-05-24 | Ongoing | 4 | 24.92 | 4.59 | 1 | 40.6 | Moyen
444 | AMR | Amr Arid | FXU | FUEL TANK | OPMOBILITY |  | 2024-12-04 | 2024-05-17 | NC | 2024-05-17 | 2024-06-28 | NC | 2024-06-28 | 2024-07-26 | NC | 2024-07-26 | 2025-10-09 | NC | 2025-10-09 | 2026-06-26 | Ongoing | 5 | 33.42 | 4.69 | 0.81 | 41.5 | Moyen
445 | AMR | Amr Arid | FXU | GLOVE BOX SWINGBIN LHD -ASSY RHD | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-02-12 | VAL | 2025-11-20 | 2026-05-24 | Ongoing | 4 | 24.92 | 4.64 | 1.03 | 41 | Moyen
446 | AMR | Amr Arid | FXU | E-CALL UNIT COVER LHD RHD ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-05-24 | Ongoing | 4 | 24.92 | 4.64 | 1.03 | 41 | Moyen
447 | AMR | Amr Arid | FXU | CLIMATE COVER MCM KEYED LHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-02-12 | VAL | 2025-11-20 | 2026-05-29 | Ongoing | 4 | 24.92 | 4.63 | 1.02 | 41 | Moyen
448 | AMR | Amr Arid | FXU | CLIMATE COVER ACM LHD-RHD ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-06-21 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
449 | AMR | Amr Arid | FXU | COLUMN COVER LOWER W/O SB PART NUMBER 73 | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-06-21 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
450 | AMR | Amr Arid | FXU | COLUMN COVER UPPER PART NUMBER 77 | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-06-21 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
451 | AMR | Amr Arid | FXU | COLUMN COVER LOWER KEYED IGNITION -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-06-21 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
452 | AMR | Amr Arid | FXU | RADIO LOWER COVER BEZEL LHD/RHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-06-19 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
453 | AMR | Amr Arid | FXU | RADIO LOWER COVER BEZEL WITH LIGHT LHD/RHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-06-19 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
454 | AMR | Amr Arid | FXU | RADIO UPPER COVER LHD/RHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-06-19 | Ongoing | 4 | 24.92 | 4.6 | 1.01 | 40.7 | Moyen
455 | AMR | Amr Arid | FXU | FACIA CTR BEZEL LT/PASS RHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-05-20 | Ongoing | 4 | 24.92 | 4.64 | 1.03 | 41.1 | Moyen
456 | AMR | Amr Arid | FXU | LSS BEZEL LHD RHD | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-05-20 | Ongoing | 4 | 24.92 | 4.64 | 1.03 | 41.1 | Moyen
457 | AMR | Amr Arid | FXU | END COVER LHS-ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-05-20 | Ongoing | 4 | 24.92 | 4.64 | 1.03 | 41.1 | Moyen
458 | AMR | Amr Arid | FXU | RADIO BEZEL CTR FACIA LHD/RHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
459 | AMR | Amr Arid | FXU | PHONE CREDEL BEZEL CTR FACIA LHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-04 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
460 | AMR | Amr Arid | FXU | CREDLE FRONT BEZEL | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
461 | AMR | Amr Arid | FXU | COLUMN COVER UPPER | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-11 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
462 | AMR | Amr Arid | FXU | UPR FACIA RT/PASS MIC LHD RHD | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-11 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
463 | AMR | Amr Arid | FXU | UPR FACIA LT/DRV MIC LHD R | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-11 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
464 | AMR | Amr Arid | FXU | UPR FACIA CTR BEZEL LHD rhd | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-11 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
465 | AMR | Amr Arid | FXU | UPR FACIA CTR BEZEL RHD | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2026-01-11 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
466 | AMR | Amr Arid | FXU | LWR FACIA RT/PASS MIC LHD | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
467 | AMR | Amr Arid | FXU | LWR FACIA RT/PASS WRAP | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
468 | AMR | Amr Arid | FXU | LWR FACIA RT/PASS WRAP LHD | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
469 | AMR | Amr Arid | FXU | IP DELIVERY LHD | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-26 | 2026-01-11 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
470 | AMR | Amr Arid | FXU | MASKING BRACKET | FORVIA | [10 empty] | 2024-08-27 | 2026-01-12 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 1 | 7.25 | 0.25 | 0.55 | 2.2 | Très faible
471 | AMR | Amr Arid | FXU | UPPER END CUP | FORVIA | [10 empty] | 2024-08-28 | 2026-01-13 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 1 | 7.25 | 0.25 | 0.55 | 2.2 | Très faible
472 | AMR | Amr Arid | FXU | DRIVER LOWER PANEL RHD LHD -ASSY | FORVIA |  | 2024-12-05 | 2024-06-16 | NC | 2024-06-16 | 2024-07-28 | NC | 2024-07-28 | 2024-08-25 | NC | 2024-08-25 | 2025-12-04 | VAL | 2025-11-20 | 2026-06-12 | Ongoing | 4 | 24.92 | 4.61 | 1.01 | 40.8 | Moyen
473 | AMR | Amr Arid | FXU | Brake pipe underbody ice/MHEV LH | COPPER |  | 2024-06-15 | 2024-07-20 | NC | 2024-07-20 | 2024-08-31 | NC | 2024-08-31 | 2024-09-28 | NC | 2024-09-28 | 2024-10-26 | NC | 2024-10-26 | 2026-06-12 | Ongoing | 5 | 33.42 | 5.82 | 0.92 | 51.5 | Moyen
474 | AMR | Amr Arid | FXU | Brake pipe BEV LH | COOPER |  | 2025-06-15 | 2025-07-20 | NC | 2025-07-20 | 2025-08-31 | NC | 2025-08-31 | 2025-09-28 | NC | 2025-09-28 | 2025-10-26 | NC | 2025-10-26 | 2026-06-12 | Ongoing | 5 | 33.42 | 5.96 | 0.98 | 52.7 | Moyen
475 | AMR | Amr Arid | FXU | FLOOR CONSOL DECO PARTS | KLC |  | 2024-06-05 | 2024-10-06 | NC | 2024-10-06 | 2024-07-22 | NC | 2024-07-22 | 2024-08-19 | NC | 2024-08-19 | 2024-09-16 | NC | 2024-09-16 | 2026-06-12 | Ongoing | 5 | 33.42 | 5.46 | 0.86 | 48.3 | Moyen
476 | AMR | Amr Arid | FXU | ARMATURE BUMPER | OPMOBILTY |  | 2024-06-17 | 2024-07-22 | NC | 2024-07-22 | 2024-02-09 | NC | 2024-02-09 | 2024-09-30 | NC | 2024-09-30 | 2025-12-09 | VAL | 2025-08-09 | 2026-06-12 | Ongoing | 4 | 24.92 | 2.24 | 0.49 | 19.8 | Très faible
477 | AMR | Amr Arid | FXU | VIZO BUMPER | OPMOBILTY |  | 2024-06-17 | 2024-07-22 | NC | 2024-07-22 | 2024-02-09 | NC | 2024-02-09 | 2024-09-30 | NC | 2024-09-30 | 2025-09-19 | VAL | 2025-09-17 | 2026-06-12 | Ongoing | 4 | 24.92 | 2.26 | 0.5 | 20 | Faible
478 | AMR | Amr Arid | fxu | HVAC | denso |  | 2024-06-18 | 2024-07-23 | NC | 2024-07-23 | 2024-03-09 | NC | 2024-03-09 | 2024-01-10 | NC | 2024-01-10 | 2024-02-16 | NC | 2025-10-10 | 2026-06-12 | Ongoing | 5 | 33.42 | 4.84 | 0.8 | 42.9 | Moyen
479 | AMR | Amr Arid | fxu | FrontFenderCladdingLH/RH | simoldes |  | 2025-07-08 | 2024-07-24 | NC | 2024-07-24 | 2024-04-09 | NC | 2024-04-09 | 2024-02-10 | NC | 2024-02-10 | 2025-12-18 | VAL | 2025-10-10 | 2026-05-10 | Ongoing | 4 | 24.92 | 4.02 | 0.88 | 35.6 | Faible
480 | AMR | Amr Arid | fxu | FrontDoorCladdingLH/RH | simoldes |  | 2025-07-08 | 2024-07-25 | NC | 2024-07-25 | 2024-05-09 | NC | 2024-05-09 | 2024-03-10 | NC | 2024-03-10 | 2025-12-18 | VAL | 2025-10-10 | 2026-05-17 | Ongoing | 4 | 24.92 | 4.01 | 0.88 | 35.5 | Faible
484 | AMR | Amr Arid | fxu | Traction motor/ Invertor/ Reducer -300/400KM | EMOTORS |  | 2025-09-17 | 1900-04-02 | VAL | 2026-01-11 | 2026-02-08 | NS | 2026-02-08 | 2026-03-08 | NS | 2026-03-08 | 2026-04-05 | NS | 2026-04-05 | 2026-06-28 | Ongoing | 4 | 30.92 | 6.52 | 1.46 | 57.7 | Moyen
485 | AMR | Amr Arid | fxu | BRAKE PEDAL MODULE | SL Poland |  | 2025-09-17 | 1900-04-02 | VAL | 2026-01-11 | 2026-02-08 | NS | 2026-02-08 | 2026-03-08 | NS | 2026-03-08 | 2026-04-05 | NS | 2026-04-05 | 2026-06-28 | Ongoing | 4 | 30.92 | 6.52 | 1.46 | 57.7 | Moyen
486 | AMR | Amr Arid | fxu | Housing cover steel upper | Comet Sud |  | 2025-09-17 | 1900-04-02 | VAL | 2026-01-11 | 2026-02-08 | NS | 2026-02-08 | 2026-03-08 | NS | 2026-03-08 | 2026-04-05 | NS | 2026-04-05 | 2026-06-28 | Ongoing | 4 | 30.92 | 6.52 | 1.46 | 57.7 | Moyen
494 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | IP BODY& ACCESSORIES ASSY |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
495 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | IP COVER ASSY LH/ IP COVER ASSY RH/ IP COVER ASSY LH/ IP COVER ASSY RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
496 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | IP COVER ASSY LH/ IP COVER ASSY RH/ IP COVER ASSY LH/ IP COVER ASSY RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
497 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | CONSOLE & ACCESSORY ASSY/ CONSOLE & ACCESSORY ASSY |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
498 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | BATTERY PACK ASSY/ BATTERY PACK ASSY |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
499 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | BATTERY PACK ASSY/ BATTERY PACK ASSY |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
500 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | SUBFRAME ASSY FRT |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
501 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | CONTROL ARM ASSY-FRT LWR SUSPENSION FRT LH/ CONTROL ARM ASSY-FRT LWR SUSPENSION FRT RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-23 | Ongoing | 2026-03-06 | 2026-04-15 | NS | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 5 | 33.42 | 5.33 | 1 | 47.1 | Moyen
502 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | CONTROL ARM ASSY-FRT LWR SUSPENSION FRT LH/ CONTROL ARM ASSY-FRT LWR SUSPENSION FRT RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-06 | VAL | 2026-03-06 | 2026-04-20 | Ongoing | 2026-04-04 | 2026-05-05 | NS | 2026-05-05 | 2026-07-28 | NS | 4 | 25.25 | 4.86 | 1.16 | 43 | Moyen
503 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STABILIZER BAR ASSY FRT |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-05 | VAL | 2025-12-05 | 2026-04-20 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-07-28 | NS | 4 | 25.25 | 2.9 | 0.74 | 25.7 | Faible
504 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY-FRT LH/ STRUT ASSY-FRT LH/ STRUT ASSY-FRT RH/ STRUT ASSY-FRT RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-05 | VAL | 2025-12-05 | 2026-04-20 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.78 | 0.67 | 24.6 | Faible
505 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY-FRT LH/ STRUT ASSY-FRT LH/ STRUT ASSY-FRT RH/ STRUT ASSY-FRT RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-05 | VAL | 2025-12-05 | 2026-04-20 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.78 | 0.67 | 24.6 | Faible
506 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY-FRT LH/ STRUT ASSY-FRT LH/ STRUT ASSY-FRT RH/ STRUT ASSY-FRT RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-04-20 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.82 | 0.68 | 25 | Faible
507 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY-FRT LH/ STRUT ASSY-FRT LH/ STRUT ASSY-FRT RH/ STRUT ASSY-FRT RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-04-15 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.84 | 0.68 | 25.1 | Faible
508 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | SUBFRAME ASSY RR |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-04-15 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.84 | 0.68 | 25.1 | Faible
509 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY RR LH/ STRUT ASSY RR LH/ STRUT ASSY RR RH/ STRUT ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-04-15 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.84 | 0.68 | 25.1 | Faible
510 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY RR LH/ STRUT ASSY RR LH/ STRUT ASSY RR RH/ STRUT ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-04-15 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.84 | 0.68 | 25.1 | Faible
511 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY RR LH/ STRUT ASSY RR LH/ STRUT ASSY RR RH/ STRUT ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-04-15 | Ongoing | 2026-03-13 | 2026-05-26 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 2.84 | 0.68 | 25.1 | Faible
512 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | STRUT ASSY RR LH/ STRUT ASSY RR LH/ STRUT ASSY RR RH/ STRUT ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-03-16 | VAL | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 3 | 18.25 | 2.35 | 0.77 | 20.8 | Faible
513 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | BRAKE PIPE ASSY 2-RR LH/ BRAKE PIPE ASSY 2-RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2025-12-19 | VAL | 2025-12-19 | 2026-03-16 | VAL | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 3 | 18.25 | 2.35 | 0.77 | 20.8 | Faible
514 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | BRAKE PIPE ASSY 2-RR LH/ BRAKE PIPE ASSY 2-RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-12 | VAL | 2026-03-12 | 2026-04-15 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 3.79 | 0.89 | 33.6 | Faible
515 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | COVER ASSY-LH COWL PLATE/ COVER ASSY-RH COWL PLATE |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-12 | VAL | 2026-03-12 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 4.1 | 0.96 | 36.3 | Faible
516 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | SPOILER ASSY |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-12 | VAL | 2026-03-12 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 4.1 | 0.96 | 36.3 | Faible
517 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR FRONT CABIN/ PROTECTOR ASSY-LWR REAR CABIN |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-12 | VAL | 2026-03-12 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 4.1 | 0.96 | 36.3 | Faible
518 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR FRONT CABIN/ PROTECTOR ASSY-LWR REAR CABIN |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-12 | VAL | 2026-03-12 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 4.1 | 0.96 | 36.3 | Faible
519 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR LH/ PROTECTOR-LWR LH/ PROTECTOR ASSY-LWR RH/ PROTECTOR-LWR RH/ PROTECTOR ASSY-LWR LH/ PROTECTOR ASSY-LWR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 3.93 | 0.92 | 34.8 | Faible
520 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR LH/ PROTECTOR-LWR LH/ PROTECTOR ASSY-LWR RH/ PROTECTOR-LWR RH/ PROTECTOR ASSY-LWR LH/ PROTECTOR ASSY-LWR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-01 | NS | 4 | 25.25 | 3.93 | 0.92 | 34.8 | Faible
521 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR LH/ PROTECTOR-LWR LH/ PROTECTOR ASSY-LWR RH/ PROTECTOR-LWR RH/ PROTECTOR ASSY-LWR LH/ PROTECTOR ASSY-LWR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 3.91 | 0.91 | 34.6 | Faible
522 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR LH/ PROTECTOR-LWR LH/ PROTECTOR ASSY-LWR RH/ PROTECTOR-LWR RH/ PROTECTOR ASSY-LWR LH/ PROTECTOR ASSY-LWR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-06-02 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 3.91 | 0.91 | 34.6 | Faible
523 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR LH/ PROTECTOR-LWR LH/ PROTECTOR ASSY-LWR RH/ PROTECTOR-LWR RH/ PROTECTOR ASSY-LWR LH/ PROTECTOR ASSY-LWR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 4.07 | 0.94 | 36 | Faible
524 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | PROTECTOR ASSY-LWR LH/ PROTECTOR-LWR LH/ PROTECTOR ASSY-LWR RH/ PROTECTOR-LWR RH/ PROTECTOR ASSY-LWR LH/ PROTECTOR ASSY-LWR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 4.07 | 0.94 | 36 | Faible
525 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 4.07 | 0.94 | 36 | Faible
526 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-04-09 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 4.07 | 0.94 | 36 | Faible
527 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 5.21 | 1.18 | 46.1 | Moyen
528 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-03-09 | VAL | 2026-03-09 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 5.21 | 1.18 | 46.1 | Moyen
529 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-15 | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 3.18 | 0.75 | 28.1 | Faible
530 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-15 | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-05-19 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 3.18 | 0.75 | 28.1 | Faible
531 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-15 | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-06-07 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 2.98 | 0.71 | 26.4 | Faible
532 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANEL ASSY FRT LH/ DOOR TRIM PANE ASSY FRT RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH/ DOOR TRIM PANE ASSY RR LH/ DOOR TRIM PANE ASSY RR RH |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-15 | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-06-07 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 2.98 | 0.71 | 26.4 | Faible
533 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | INR TRIM ASSY-LWR TAIL DOOR |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-15 | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-06-07 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 2.98 | 0.71 | 26.4 | Faible
534 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | INR TRIM ASSY-UPR TAIL DOOR/ TRIM PANEL ASSY-LH TAILGATE/ TRIM PANEL ASSY-RH TAILGATE |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-15 | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-06-07 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 2.98 | 0.71 | 26.4 | Faible
535 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | INR TRIM ASSY-UPR TAIL DOOR/ TRIM PANEL ASSY-LH TAILGATE/ TRIM PANEL ASSY-RH TAILGATE |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-15 | VAL | 2026-01-15 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-06-07 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 2.98 | 0.71 | 26.4 | Faible
536 | RHIZLANE | RHIZLANE BELMABKHOUT | B10 | INR TRIM ASSY-UPR TAIL DOOR/ TRIM PANEL ASSY-LH TAILGATE/ TRIM PANEL ASSY-RH TAILGATE |  | Ongoing |  |  | NC | 2025-09-29 | 2026-01-29 | VAL | 2026-01-29 | 2026-03-27 | Ongoing | 2026-03-13 | 2026-06-07 | NS | 2026-04-15 | 2026-09-08 | NS | 4 | 25.25 | 3.15 | 0.75 | 27.9 | Faible
537 | IMANE | IMANE BOULAHIA | O1H | O1H - Rearlamp | TBD | Canceled | 2025-02-04 | 2025-09-28 | VAL | 2025-02-05 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 4 | 30.92 | 1.51 | 0.32 | 13.4 | Très faible
538 | IMANE | IMANE BOULAHIA | O1H | O1H - Rearlamp | TBD | Canceled | 2025-02-04 | 2025-09-28 | VAL | 2025-02-05 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 4 | 30.92 | 1.51 | 0.32 | 13.4 | Très faible
539 | IMANE | IMANE BOULAHIA | O1H | O1H - Headlamp | TBD | Canceled | 2025-02-04 | 2025-09-28 | VAL | 2025-09-16 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 4 | 30.92 | 1.69 | 0.35 | 15 | Très faible
540 | IMANE | IMANE BOULAHIA | P1X | P1X - Rearlamp | TBD | Canceled | 2025-04-23 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-05-15 | NC | 5 | 33.42 | 1.77 | 0.29 | 15.7 | Très faible
541 | IMANE | IMANE BOULAHIA | O1H | O1H-SP2785-FINISHER INNER GUSSET DOOR RH-LH | TBD | Canceled | 2025-05-14 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 5 | 33.42 | 1.8 | 0.3 | 15.9 | Très faible
542 | IMANE | IMANE BOULAHIA | O1H | O1H-SP2786-SWITCH BEZEL Passenger | TBD | Canceled | 2025-05-14 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 5 | 33.42 | 1.8 | 0.3 | 15.9 | Très faible
543 | IMANE | IMANE BOULAHIA | O1H | O1H-SP2787-SWITCH BEZEL DRIVER | TBD | Canceled | 2025-05-14 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 5 | 33.42 | 1.8 | 0.3 | 15.9 | Très faible
544 | IMANE | IMANE BOULAHIA | O1H | O1H-SP2788-SWITCH BEZEL All Levels RR (LH) (RH) | TBD | Canceled | 2025-05-14 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 5 | 33.42 | 1.8 | 0.3 | 15.9 | Très faible
545 | IMANE | IMANE BOULAHIA | O1H | Aerofin /O1H Aerofin LH-RH | TBD | Canceled | 2025-05-14 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 5 | 33.42 | 1.8 | 0.3 | 15.9 | Très faible
546 | IMANE | IMANE BOULAHIA | O1H | Embelisher /O1H side embelisher LH-RH | TBD | Canceled | 2025-05-21 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 5 | 33.42 | 1.8 | 0.3 | 16 | Très faible
547 | IMANE | IMANE BOULAHIA | P1X | P1X Aerofin | TBD | Canceled | 2025-02-07 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-05-15 | NC | 5 | 33.42 | 1.75 | 0.29 | 15.5 | Très faible
548 | IMANE | IMANE BOULAHIA | P1X | P1X Spoiler | TBD | Canceled | 2025-02-07 | 2025-11-28 | NC | 2025-09-28 | 2026-03-15 | NC | 2026-03-15 | 2026-10-15 | NC | 2026-10-15 | 2026-12-12 | NC | 2026-12-12 | 2028-05-15 | NC | 5 | 33.42 | 1.75 | 0.29 | 15.5 | Très faible
549 | IMANE | IMANE BOULAHIA | P1H | REAR TINTED FIXED GLASS/REAR OVER-TINTED FIXED GLASS | Hutchinson | Ongoing |  | 1900-04-02 | NC | 2025-04-04 | 2025-10-10 | VAL | 2025-10-17 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.46 | 0.56 | 21.7 | Faible
550 | IMANE | IMANE BOULAHIA | P1H | REAR GLASS RUN CHANNEL MATTE BLACK | Hutchinson | Ongoing |  | 1900-04-02 | NC | 2025-04-04 | 2025-11-30 | VAL | 2025-10-17 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NC | 2026-12-12 | 2027-07-06 | NC | 4 | 25.25 | 2.46 | 0.56 | 21.7 | Faible
551 | IMANE | IMANE BOULAHIA | P1HP1H/O1H/P1X | FRONT GLASS RUN CHANNEL MATTE BLACK | Hutchinson | Ongoing |  | 1900-04-02 | NC | 2025-04-04 | 2025-11-30 | VAL | 2025-10-17 | 2026-04-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.49 | 0.57 | 22.1 | Faible
552 | IMANE | IMANE BOULAHIA | P1H/O1H | SPOILER - Grained/Black Mirror | OP MObility | Ongoing |  | 1900-04-02 | NC | 2025-05-23 | 2026-04-21 | Ongoing | 2026-08-02 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 3.56 | 0.64 | 31.5 | Faible
553 | IMANE | IMANE BOULAHIA | P1H/O1H | TAILGATE EMBELLISHER - GRAINED/BLACK MIRROR | OP Mobility | Ongoing |  | 1900-04-02 | NC | 2025-05-23 | 2026-04-21 | Ongoing | 2026-08-02 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 3.56 | 0.64 | 31.5 | Faible
554 | IMANE | IMANE BOULAHIA | P1H | Headliner Normal roof for ENTRY version/ Headliner Normal | Howa Tramico | Ongoing |  | 1900-04-02 | NC | 2025-04-23 | 2026-01-27 | VAL | 2025-10-14 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.45 | 0.56 | 21.7 | Faible
555 | IMANE | IMANE BOULAHIA | P1H | Headliner Cielo roof | Howa Tramico | Ongoing |  | 1900-04-02 | NC | 2025-04-23 | 2026-01-27 | VAL | 2025-10-14 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.45 | 0.56 | 21.7 | Faible
556 | IMANE | IMANE BOULAHIA | P1H/P1X | Headlamp R/L/RHD/LHD/Mainstream/Upper | OP MObility | Ongoing |  | 1900-04-02 | NC | 2025-08-05 | 2025-12-07 | CANCELED | 2025-11-18 | 2026-07-04 | CANCELED | 2026-07-04 | 2026-12-12 | CANCELED | 2026-12-12 | 2027-07-06 | CANCELED | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
557 | IMANE | IMANE BOULAHIA | P1H | Illuminated Grid UPPER P1H | OP MObility | Ongoing |  | 1900-04-02 | NC | 2025-07-15 | 2026-03-01 | VAL | 2025-11-18 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.5 | 0.57 | 22.1 | Faible
558 | IMANE | IMANE BOULAHIA | P1H | REARLAMP R/L | Marelli | Ongoing |  | 1900-04-02 | NC | 2025-11-04 | 2025-10-10 | VAL | 2025-07-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.38 | 0.55 | 21.1 | Faible
559 | IMANE | IMANE BOULAHIA | P1H | CENTRAL REARLAMP | Marelli | Ongoing |  | 1900-04-02 | NC | 2025-11-04 | 2025-10-10 | VAL | 2025-07-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.38 | 0.55 | 21.1 | Faible
560 | IMANE | IMANE BOULAHIA | P1H | Front Carpet RHD/LHD/ Front Carpet RHD/LHD + Driving | Treves | Ongoing |  | 1900-04-02 | NC | 2025-07-05 | 2026-03-21 | VAL | 2025-04-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.34 | 0.54 | 20.8 | Faible
561 | IMANE | IMANE BOULAHIA | P1H | Inner Dash cockpit side LHD/RHD + driving school | Treves | Ongoing |  | 1900-04-02 | NC | 2025-07-05 | 2026-03-21 | VAL | 2025-04-10 | 2026-04-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.35 | 0.54 | 20.8 | Faible
562 | IMANE | IMANE BOULAHIA | P1H | back closure embellisher RH/LH P1H | Maeir | Ongoing |  | 1900-04-02 | NC | 2025-03-14 | 2026-01-27 | VAL | 2025-04-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.34 | 0.54 | 20.8 | Faible
563 | IMANE | IMANE BOULAHIA | P1H/P1X | Front/Rear B pillar exterior door trim RH/LH P1H O1H /P1X | Maeir | Ongoing |  | 1900-04-02 | NC | 2025-03-14 | 2026-01-27 | VAL | 2025-04-10 | 2026-04-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.35 | 0.54 | 20.8 | Faible
564 | IMANE | IMANE BOULAHIA | P1H | Windshield | Saint Gobain | Ongoing |  | 1900-04-02 | NC | 2025-09-05 | 2025-10-10 | VAL | 2025-09-25 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.43 | 0.56 | 21.5 | Faible
565 | IMANE | IMANE BOULAHIA | P1H | Backlite | AGC | Ongoing |  | 1900-04-02 | NC | 2025-05-22 | 2026-04-21 | Ongoing | 2025-11-30 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.75 | 0.5 | 24.4 | Faible
566 | IMANE | IMANE BOULAHIA | P1H | Fixed roof glass | AGC | Ongoing |  | 1900-04-02 | NC | 2025-08-05 | 2025-12-01 | VAL | 2025-09-25 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.43 | 0.56 | 21.5 | Faible
567 | IMANE | IMANE BOULAHIA | P1H | FR Wheel arch trim | SMP | Ongoing |  | 1900-04-02 | NC | 2025-04-14 | 2026-01-27 | VAL | 2025-11-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.49 | 0.57 | 22 | Faible
568 | IMANE | IMANE BOULAHIA | P1H | RR Wheel arch trim | SMP | Ongoing |  | 1900-04-02 | NC | 2025-04-14 | 2026-01-27 | VAL | 2025-11-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.49 | 0.57 | 22 | Faible
569 | IMANE | IMANE BOULAHIA | P1H | Gusset Embellisher | Forvia | Ongoing |  | 1900-04-02 | NC | 2025-05-14 | 2025-11-30 | VAL | 2025-10-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.45 | 0.56 | 21.7 | Faible
570 | IMANE | IMANE BOULAHIA | P1H | Finisher switch driver RHD-LHD | Forvia | Ongoing |  | 1900-04-02 | NC | 2025-05-14 | 2025-11-30 | VAL | 2025-10-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.45 | 0.56 | 21.7 | Faible
571 | IMANE | IMANE BOULAHIA | P1H | Finisher switch passenger RHD-LHD | Forvia | Ongoing |  | 1900-04-02 | NC | 2025-05-14 | 2025-11-30 | VAL | 2025-10-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.45 | 0.56 | 21.7 | Faible
572 | IMANE | IMANE BOULAHIA | P1H | Rear switch finisher | Forvia | Ongoing |  | 1900-04-02 | NC | 2025-05-14 | 2025-11-30 | VAL | 2025-10-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.45 | 0.56 | 21.7 | Faible
573 | IMANE | IMANE BOULAHIA | P1H | PULL CUP SCREW CAP FRONT RH/LH | Forvia | Ongoing | 2025-06-16 | 2025-07-21 | VAL | 2025-04-07 | 2025-11-30 | VAL | 2025-10-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 3 | 22.75 | 1.2 | 0.42 | 10.6 | Très faible
574 | IMANE | IMANE BOULAHIA | P1H | PULL CUP SCREW CAP REAR RH/LH | Forvia | Ongoing | 2025-06-16 | 2025-07-21 | VAL | 2025-04-07 | 2025-11-30 | VAL | 2025-10-10 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 3 | 22.75 | 1.2 | 0.42 | 10.6 | Très faible
575 | IMANE | IMANE BOULAHIA | P1H | IP-DRIVER UNDER FACIA PANEL LINING | SMRC | Ongoing |  | 1900-04-02 | NC | 2025-03-20 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24.1 | Faible
576 | IMANE | IMANE BOULAHIA | P1H | IP-PASSENGER UNDER FACIA PANEL LINING | SMRC | Ongoing |  | 1900-04-02 | NC | 2025-03-20 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24.1 | Faible
577 | IMANE | IMANE BOULAHIA | P1H | IP-FACADE DIFFUSER CENT | SMRC | Ongoing |  | 1900-04-02 | NC | 2025-03-20 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24.1 | Faible
578 | IMANE | IMANE BOULAHIA | P1H | IP-FACADE LH/RH FACIA PANEL | SMRC | Ongoing |  | 1900-04-02 | NC | 2025-03-20 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24.1 | Faible
579 | IMANE | IMANE BOULAHIA | P1H | FINISHER TOP CONSOLE | SMRC | Ongoing |  | 1900-04-02 | NC | 2025-03-20 | 2025-12-22 | CANCELED | 2025-11-29 | 2026-07-04 | CANCELED | 2026-07-04 | 2026-12-12 | CANCELED | 2026-12-12 | 2027-07-06 | CANCELED | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
580 | IMANE | IMANE BOULAHIA | P1H | 01/101 FACIA PANEL UPR ASS | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-03-22 | VAL | 2025-11-29 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.52 | 0.58 | 22.3 | Faible
581 | IMANE | IMANE BOULAHIA | P1H | 02/102 FACIA PANEL LWR | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-03-22 | VAL | 2025-11-29 | 2026-05-15 | Ongoing | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 25.25 | 2.52 | 0.58 | 22.3 | Faible
582 | IMANE | IMANE BOULAHIA | P1H | 03-A HALF-SHEAFT FUSE BD (MECA) | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24 | Faible
583 | IMANE | IMANE BOULAHIA | P1H | 03-B HALF-SHEAFT FUSE BD (SBW) | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24 | Faible
584 | IMANE | IMANE BOULAHIA | P1H | 05-A ENS STEERING COLUMN HALF-SHEAFT (MECA) | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24 | Faible
585 | IMANE | IMANE BOULAHIA | P1H | 05-B ENS STEERING COLUMN HALF-SHEAFT (SBW) | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24 | Faible
586 | IMANE | IMANE BOULAHIA | P1H | U8 ARMATURE RR LEFT ASS | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24 | Faible
587 | IMANE | IMANE BOULAHIA | P1H | U3/U4 PANEL FRT LH CONSOLE | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-04-21 | Ongoing | 2025-11-29 | 2026-04-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.72 | 0.49 | 24 | Faible
588 | IMANE | IMANE BOULAHIA | P1H | E13/E14 PANEL FRT LH CONSOLE | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-03-07 | CANCELED | 2025-11-29 | 2026-04-15 | CANCELED | 2026-07-04 | 2026-09-24 | CANCELED | 2026-12-12 | 2027-07-06 | CANCELED | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
589 | IMANE | IMANE BOULAHIA | P1H | E18/E19 PANEL RR LH CONSOLE | Novares | Ongoing |  | 1900-04-02 | NC | 2025-02-25 | 2026-03-07 | CANCELED | 2025-11-29 | 2026-04-15 | CANCELED | 2026-07-04 | 2026-09-24 | CANCELED | 2026-12-12 | 2027-07-06 | CANCELED | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
590 | IMANE | IMANE BOULAHIA | P1H | CONTROL PANEL | PREH | Canceled |  | 1900-04-02 | NC | 2025-04-14 | 2026-02-14 | CANCELED | 2025-12-14 | 2026-07-04 | CANCELED | 2026-07-04 | 2026-12-12 | CANCELED | 2026-12-12 | 2027-07-06 | CANCELED | 1 | 2.5 | 1.25 | 1 | 11.1 | Très faible
591 | IMANE | IMANE BOULAHIA | O1H | ASM Cover Uplevel Front Compartment painted, LHD / RHD | TBD | CANCELED | 2025-05-28 | 2025-11-28 | NC | 2025-09-28 | 2026-03-14 | NC | 2026-03-14 | 2026-06-06 | NC | 2026-06-06 | 2026-12-12 | NC | 2026-12-12 | 2028-02-17 | NC | 5 | 33.42 | 1.45 | 0.26 | 12.9 | Très faible
592 | IMANE | IMANE BOULAHIA | P1X | Front Carpet RHD/LHD | Componentes Porrino | Ongoing |  |  | NC | 2025-10-28 | 2026-05-12 | Ongoing | 2026-03-11 | 2026-04-15 | NS | 2026-08-29 | 2026-09-24 | NS | 2026-12-12 | 2028-02-17 | NS | 5 | 33.42 | 5.35 | 0.86 | 47.3 | Moyen
593 | IMANE | IMANE BOULAHIA | P1X | Inner Dash cockpit side LHD/RHD + driving school | Componentes Porrino | Ongoing |  |  | NC | 2025-10-29 | 2026-05-12 | Ongoing | 2026-03-11 | 2026-04-15 | NS | 2026-08-29 | 2026-09-24 | NS | 2026-12-12 | 2028-02-17 | NS | 5 | 33.42 | 5.35 | 0.86 | 47.4 | Moyen
594 | IMANE | IMANE BOULAHIA | P1X | Gusset Embellisher | SIMOLDES | Ongoing |  |  | NC | 2025-10-30 | 2026-05-12 | Ongoing | 2026-03-11 | 2026-04-15 | NS | 2026-08-29 | 2026-09-24 | NS | 2026-12-12 | 2028-02-17 | NS | 5 | 33.42 | 5.35 | 0.86 | 47.4 | Moyen
595 | IMANE | IMANE BOULAHIA | P1X | Finisher switch driver RHD-LHD | SIMOLDES | Ongoing |  |  | NC | 2025-10-31 | 2026-05-12 | Ongoing | 2026-03-11 | 2026-04-15 | NS | 2026-08-29 | 2026-09-24 | NS | 2026-12-12 | 2028-02-17 | NS | 5 | 33.42 | 5.35 | 0.86 | 47.4 | Moyen
596 | IMANE | IMANE BOULAHIA | P1X | Finisher switch passenger RHD-LHD | SIMOLDES | Ongoing |  |  | NC | 2025-11-01 | 2026-05-12 | Ongoing | 2026-03-11 | 2026-04-15 | NS | 2026-08-29 | 2026-09-24 | NS | 2026-12-12 | 2028-02-17 | NS | 5 | 33.42 | 5.35 | 0.86 | 47.4 | Moyen
597 | IMANE | IMANE BOULAHIA | P1X | Rear switch finisher | SIMOLDES | Ongoing |  |  | NC | 2025-11-02 | 2026-05-12 | Ongoing | 2026-03-11 | 2026-04-15 | NS | 2026-08-29 | 2026-09-24 | NS | 2026-12-12 | 2028-02-17 | NS | 5 | 33.42 | 5.36 | 0.86 | 47.4 | Moyen
598 | IMANE | IMANE BOULAHIA | P1X | Headliner Normal roof for ENTRY version/ Headliner Normal | Howa Tramico | Ongoing |  | 1900-04-02 | NC | 2025-04-23 | 2026-06-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.5 | 0.46 | 22.2 | Faible
599 | IMANE | IMANE BOULAHIA | P1X | Headliner Cielo roof | Howa Tramico | Ongoing |  | 1900-04-02 | NC | 2025-04-23 | 2026-06-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.5 | 0.46 | 22.2 | Faible
600 | IMANE | IMANE BOULAHIA | O1H | Headliner Normal roof for ENTRY version/ Headliner Normal | Howa Tramico | Ongoing |  | 1900-04-02 | NC | 2025-04-23 | 2026-07-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.5 | 0.45 | 22.1 | Faible
601 | IMANE | IMANE BOULAHIA | O1H | Headliner Cielo roof | Howa Tramico | Ongoing |  | 1900-04-02 | NC | 2025-04-23 | 2026-07-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.5 | 0.45 | 22.1 | Faible
602 | IMANE | IMANE BOULAHIA | P1X | REAR TINTED FIXED GLASS/REAR OVER-TINTED FIXED GLASS | HUTCHINSON | Ongoing |  | 1900-04-03 | NC | 2025-04-23 | 2026-05-12 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.52 | 0.46 | 22.3 | Faible
603 | IMANE | IMANE BOULAHIA | P1X | REAR GLASS RUN CHANNEL MATTE BLACK | HUTCHINSON | Ongoing |  | 1900-04-04 | NC | 2025-04-23 | 2026-05-12 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.52 | 0.46 | 22.3 | Faible
604 | IMANE | IMANE BOULAHIA | O1H | REAR TINTED FIXED GLASS/REAR OVER-TINTED FIXED GLASS | HUTCHINSON | Ongoing |  | 1900-04-05 | NC | 2025-04-23 | 2026-07-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.5 | 0.45 | 22.1 | Faible
605 | IMANE | IMANE BOULAHIA | O1H | REAR GLASS RUN CHANNEL MATTE BLACK | HUTCHINSON | Ongoing |  | 1900-04-06 | NC | 2025-04-23 | 2026-07-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.5 | 0.45 | 22.1 | Faible
606 | IMANE | IMANE BOULAHIA | P1X | WINSHIELD P1X | AGC | Ongoing |  | 1900-04-09 | NC | 2025-04-23 | 2026-07-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 5 | 33.42 | 2.5 | 0.45 | 22.1 | Faible
607 | IMANE | IMANE BOULAHIA | O1H | Backlite | AGC | Ongoing |  |  |  | 2025-04-23 | 2026-07-14 | Ongoing | 2025-10-14 | 2026-09-15 | NS | 2026-07-04 | 2026-09-24 | NS | 2026-12-12 | 2027-07-06 | NS | 4 | 30.92 | 1.25 | 0.32 | 11 | Très faible

## phase_params
phase | duration_hrs | delai_weeks | weight | Hours per week at standard pace (Durée/Délai)
advanced | 2.5 | 2 | 22% | 1.25
digital | 8.17 | 6 | 21% | 1.3617
static | 7 | 6 | 18% | 1.1667
dynamic | 8.5 | 6 | 21% | 1.4167
delivery | 7.25 | 16 | 18% | 0.45312

## persons
ca_sheet | ca_display | active | n_topics
MANAL | MANAL EL ARGOUBI | 1 | 33
Soumaya | Soumaya el boustani | 1 | 74
CHAIMAA | CHAIMAA BOUATROUSS | 0 | 0
MOFIDA | MOFIDA EL HABTI | 1 | 44
Ayoub | Ayoub Himich | 1 | 22
KHALID | KHALID BOUHLAL | 1 | 7
KENZA | KENZA AADAM | 1 | 12
MSALHA | MERIEM BENHAFID | 1 | 79
SKN | SOUKAINA EL OIRDI | 1 | 135
AMR | Amr Arid | 1 | 87
RHIZLANE | RHIZLANE BELMABKHOUT | 1 | 43
IMANE | IMANE BOULAHIA | 1 | 71
Fatimaezahra | Fatimaezahra | 0 | 0
SAFOUANE | SAFOUANE | 0 | 0

## config
key | value | description
today | 2026-04-24 | Anchor date for all calculations
weekly_capacity_hrs | 40 | Full-time week
overload_threshold | 1 | Workload fraction above which a CA is overloaded (1.0 = 100%)
underload_threshold | 0.4 | Workload fraction below which a CA is under-utilised
catchup_window_weeks | 4 | Overdue tasks are spread over ≥ this many weeks from today
stale_threshold_weeks | 12 | Phases whose end date is older than this (and status ≠ VAL) are excluded
forecast_horizon_weeks | 78 | How many weeks to forecast forward

## complexity_doc
Field | Description
n_active_phases | Phases whose status is not VAL / CANCELED / Closed / blank. Counts only "remaining work".
remaining_hours | Sum of phase_params.duration_hrs over the active phases of this topic. Standard total = 33.42 h.
weekly_load_hrs | Hours per week this topic costs its CA at its planned pace. Per phase: duration_hrs / actual_weeks (using topic dates), or duration_hrs / standard delai_weeks if dates are missing/invalid. Summed across active phases.
avg_compression | Mean of (standard delai_weeks / actual delai_weeks) across active phases. >1 = topic is more compressed than standard, <1 = more relaxed. Clipped to [0.25, 4.0].
complexity_score | 0–100 normalized: weekly_load_hrs / 5.65 × 50, capped at 100. 50 = a fresh topic at standard pace through all 5 phases (= 5.65 h/week).
complexity_level | Bucket: Très faible <20, Faible 20–40, Moyen 40–60, Fort 60–80, Très fort ≥80. N/A = no active phases (topic done/canceled).
Notes
Inverted dates | 167 phases had end_date < start_date in source data → fallback to standard delai for those phases. Recommend cleaning at source.
Status normalisation | Treats VAL, CANCELED, Canceled, Closed, closed all as "done/dead" so they do not contribute to remaining load.